qTest Consolidation – Concise Migration Plan

HS qTest → controlled export package → HCSC qTest

# 1. Executive View

The migration uses a file-mediated export/import process. Discovery is complete and provides the source inventory, hierarchy and relationships. The project is currently in the POC Export Package phase. The POC will export a reduced but representative set of related qTest artifacts, store/transfer the package through the approved shared location, import it into an HCSC qTest test project with Python/API scripts, and validate fidelity before full migration.

Connectivity/access to both HS qTest and HCSC qTest has been tested successfully for the migration tooling. This should not be interpreted as direct qTest-to-qTest connectivity: the migration remains export → file storage/transfer → import.

# 2. Simplified Migration Plan and Current Status

| # | Phase | Status | What Happens | Gate / Output |
| --- | --- | --- | --- | --- |
| 1 | Discovery & Source Assessment | Complete | Inventory elements, hierarchy, relationships, configuration and volumes. | Versioned discovery baseline. |
| 2 | POC Export Package | CURRENT | Select representative scope; export JSON/CSV/files and attachments; preserve source IDs. | Validated POC package. |
| 3 | POC Import & Transformation | Open | Map fields/users/Jira references; import in dependency order; retain source-to-target IDs. | POC recreated in HCSC test project. |
| 4 | POC Validation & Client Approval | Open | Reconcile content, hierarchy, relationships and attachments; document limitations; demo to client. | POC GO/NO-GO. |
| 5 | Target Configuration & Dependencies | Open / Parallel | Complete HCSC licensing, permissions, groups/profiles, target configuration and secure transfer readiness. | Target ready for rehearsal/full migration. |
| 6 | Full Import Tooling & Rehearsal | Open | Harden POC scripts for approved full scope; add retry/logging/checkpoints; execute rehearsal. | Accepted rehearsal. |
| 7 | Final Export & Import | Open | Refresh/freeze source, create final package, transfer and import using tested runbook. | Final import complete. |
| 8 | Final Validation & Acceptance | Open | Final reconciliation, integration/Jira checks, exception review and stakeholder sign-off. | Formal acceptance. |

# 3. POC Flow

Discovery outputs → select reduced connected scope → export HS qTest data/relationships → store package in approved SharePoint/shared storage → HCSC-side script reads package → transform/map → import into HCSC test project → rebuild supported relationships → reconcile against HS baseline → document gaps/limitations → client demonstration → GO/NO-GO.

POC acceptance should verify the same core objects already identified in the acceptance criteria: modules, non-Jira requirements, Jira-backed requirements through the integration, test cases/steps/attachments, requirement↔test-case traceability, releases/test plans, cycles, suites, runs and execution logs.

# 4. Dependencies – Current Review

The project should track only dependencies that can materially block the POC, rehearsal, or final migration. Identity synchronization is already in place, but HCSC qTest authorization remains a separate prerequisite.

| ID | Dependency | Status | Why It Matters | Next Action |
| --- | --- | --- | --- | --- |
| D-001 | HCSC qTest licensing and permissions | Open | HS users can use the HCSC AD identity, but still require qTest licenses and target authorization. | Confirm license availability, assign permissions, and validate representative user access. |
| D-002 | HS permission groups / profiles assessment | Open | Required HS groups/profiles may need to be recreated in HCSC qTest. | Determine whether HS group/profile/permission information can be extracted using available qTest API/SCIM/admin methods; recreate only required groups. |
| D-003 | HCSC target project and API write access | Open | The POC importer needs a configured target project and credentials with create/update permissions. | Confirm project configuration and API write access before POC import. |
| D-004 | SharePoint migration storage and access | Open | SharePoint is the controlled exchange point for export packages, mappings, attachments, and logs. | Connectivity/access path has been tested; confirm operational permissions, retention, and end-to-end package handling. |
| D-005 | Final Jira source-to-target mapping | Open | Destination Jira projects may change during the project. | Keep mappings external/configurable and finalize them before final migration. |

# 5. Simplified RAID

The RAID is intentionally limited to the items most useful for stakeholder decisions and weekly status review. Detailed implementation work remains in Jira and the technical workstream.

| Type | Item | Priority / Status | Response |
| --- | --- | --- | --- |
| Risk | API / version compatibility | High | POC validates supported objects and documents transformations or limitations. |
| Risk | Permission fidelity | High | Inventory required HS groups/profiles and agree the HCSC authorization model. |
| Risk | Partial import / duplicate data | High | Use persistent ID mapping, checkpoints, reconciliation, and safe rerun controls. |
| Risk | Jira project changes | Medium | Keep Jira mapping external to migration scripts and reconcile late. |
| Assumption | HS user identity reuse | To Validate | HS users are synchronized with HCSC AD; validate qTest provisioning after licenses/permissions are assigned. |
| Assumption | SharePoint operating model | To Validate | Validate approved storage access, retention, and package controls. |
| Issue | No active blocker confirmed | Monitoring | Open prerequisites remain dependencies until they actually block progress. |

# 6. Minimal Tracking Tasks

| ID | Tracking Task | Status | Done When |
| --- | --- | --- | --- |
| T1 | POC scope & export package | In Progress | Finalize representative scope and generate validated export package. |
| T2 | HCSC POC readiness | Open | Confirm target project/API plus HCSC licensing and required permissions. |
| T3 | Identity / permission groups | Open | Validate representative HS users and determine/recreate required HS groups/profiles. |
| T4 | POC import + validation | Open | Run importer, reconciliation and client demonstration; obtain GO/NO-GO. |
| T5 | Full tooling + rehearsal | Open | Harden approved POC approach and complete rehearsal after target dependencies are ready. |
| T6 | Final migration + acceptance | Open | Final refresh/import, reconciliation, exceptions and stakeholder sign-off. |

# 7. Stakeholder Timeline

Timeline dependency focus: HCSC licensing/permissions, permission-group assessment, target project/API access, SharePoint operational readiness, and final Jira mapping run in parallel and must close by their required gates.

| Target Window | Phase | Status | Focus |
| --- | --- | --- | --- |
| 07–11 Sep | Discovery baseline | Complete | Discovery outputs available and reused. |
| 12–18 Sep | POC scope & export package | CURRENT | Representative package completed and validated. |
| 19–30 Sep | POC import + validation | Next | Import into HCSC test project, reconcile, client demo and GO/NO-GO. |
| 16 Sep–02 Oct | Target dependencies (parallel) | In Progress / Open | Licenses, permissions, groups/profiles, API/project readiness, SharePoint and Jira mapping approach. |
| 01–14 Oct | Full tooling + rehearsal | Planned | Harden scripts and execute rehearsal after POC approval/readiness. |
| 15–23 Oct | Final export & import | Planned | Refresh/freeze HS package and execute tested import. |
| 24–31 Oct | Final validation & acceptance | Planned | Reconciliation, exceptions and stakeholder sign-off. |

# 8. Documentation Review Notes

The Migration Elements Status and Acceptance Criteria are the strongest qTest-specific planning sources. The Test Strategy provides useful success/entry/exit concepts but contains residual NeoLoad wording and should be corrected. The file titled 'qTest Migration Technical Plan' contains GitHub-specific migration content (GEI, repositories, runners, GitHub Apps, OIDC, etc.) and should not be used as the qTest technical plan without replacement.

The attached critical-path workbook currently uses a 07-Sep-2026 start and calculates completion on 13-Oct-2026. For stakeholder planning, the timeline above preserves the current POC position and uses 31-Oct-2026 as the overall target, leaving room for dependency closure, rehearsal, final migration and acceptance.