## Timeline
qTest Consolidation – Configurable Timeline
Planning Input | Value |  | Editable cells are highlighted in yellow. Change the Project Start Date and/or the Duration (Days) for any phase. All following dates recalculate automatically. Durations use calendar days, including weekends.
Project Start Date | 2026-09-07
Target End Date | 2026-10-31
Total Planned Days | 51
# | Migration Phase | Status | Duration (Days) | Start Date | Finish Date | Dependency / Gate | Owner | Main Output
1 | Discovery & Source Assessment | Complete | 5 | 2026-09-07 | 2026-09-11 | Project start | ELEKS qTest Migration Team | Discovery baseline
2 | POC Export Package | In Progress | 7 | 2026-09-12 | 2026-09-18 | Discovery complete | ELEKS qTest Migration Team | Validated POC export package
3 | POC Import & Transformation | Open | 10 | 2026-09-19 | 2026-09-28 | POC package + HCSC readiness | ELEKS qTest Migration Team | POC imported with ID mappings
4 | POC Validation & Client Approval | Open | 5 | 2026-09-29 | 2026-10-03 | POC import complete | POC Lead / QA Lead | POC GO / NO-GO
5 | Target Configuration & Dependencies | Open | 6 | 2026-10-04 | 2026-10-09 | POC approval / parallel readiness | HCSC qTest Admin / Owners | Licensing, permissions, groups and mappings ready
6 | Full Import Tooling & Rehearsal | Open | 8 | 2026-10-10 | 2026-10-17 | POC GO + target readiness | ELEKS qTest Migration Team | Accepted rehearsal
7 | Final Export & Import | Open | 6 | 2026-10-18 | 2026-10-23 | Accepted rehearsal | ELEKS qTest Migration Team | Final import complete
8 | Final Validation & Acceptance | Open | 4 | 2026-10-24 | 2026-10-27 | Final import complete | QA / Business Owners | Formal acceptance
Schedule Summary |  |  | Plan finishes 4 day(s) before the target date.
Calculated Start | 2026-09-07
Calculated Finish | 2026-10-27
Target End Date | 2026-10-31
Variance to Target (Days) | 4
Formulas:
Start Date = [Finish Date, row above]+1
Finish Date = [Start Date]+[Duration (Days)]-1