## Risks
qTest Consolidation — RAID Log: Risks
Potential future events that could negatively affect the HS qTest export / HCSC qTest import initiative.
Risk ID | Track | Category | Risk Description | Status | Likelihood | Impact | Priority | Owner | Mitigation / Response Plan | Dependency / Trigger | Notes
R-001 | qTest | Technical | HS and HCSC qTest API/version differences may limit migration fidelity. | In Progress | High | High | Critical | ELEKS qTest Migration Team | Validate supported objects in the POC and document required transformations/limitations. | POC API validation
R-002 | qTest | Identity / Access | HCSC licensing, permissions, or required HS-equivalent groups may not be ready for migrated users. | Open | Medium | High | High | HCSC qTest Admin / IAM | Confirm licenses and user access; inventory required HS groups/profiles and recreate only those needed in HCSC. | Target readiness
R-003 | qTest | Technical | Partial imports or reruns may create missing or duplicate HCSC data. | Open | Medium | High | High | ELEKS qTest Migration Team | Retain source-to-target ID mappings, checkpoints, reconciliation, and safe rerun controls. | Importer development
R-004 | qTest | Integration | Jira target mappings may change before final migration. | Open | Medium | Medium | Medium | Jira Integration Owner | Keep Jira mappings external to the scripts and finalize/reconcile them late. | Jira mapping

## Assumptions
qTest Consolidation — RAID Log: Assumptions
Planning assumptions that must be validated as the POC and full plan progress.
Assumption ID | Category | Assumption Description | Impact if Invalid | Owner | Validation Plan | Status | Date Identified | Target Validation Date | Date Validated | Notes
A-001 | Identity | HS users are already synchronized with HCSC Active Directory and can use the same enterprise identity. | Users may require alternate provisioning or mapping before they can access HCSC qTest. | HCSC IAM / qTest Admin | Validate login/provisioning for representative HS users after qTest licensing and permissions are assigned. | In Progress
A-002 | Architecture | Migration remains file-mediated: HS qTest export package is stored/transferred through approved SharePoint storage and then imported into HCSC qTest. | The migration operating model and scripts would need redesign. | Project Lead / Platform | Validate end-to-end SharePoint access and package handling from both migration sides. | Validated
A-003 | Planning | Discovery outputs remain the baseline for POC scope, full migration planning, and reconciliation. | Additional discovery/rework may be required. | ELEKS qTest Migration Team | Version and retain the discovery outputs used by the POC. | Validated

## Issues
qTest Consolidation — RAID Log: Issues
Current problems requiring active resolution.
Issue ID | Track | Category | Issue Description | Impact | Priority | Owner | Resolution Plan | Status | Date Raised | Target Resolution Date | Date Resolved | Notes
I-001 | qTest | Project | No active blocking issue is currently confirmed; open prerequisites are tracked as dependencies. | No current migration stop. | Low | Project Lead | Review weekly and convert any failed/overdue dependency into an active issue when it blocks progress. | Monitoring

## Dependencies
qTest Consolidation — RAID Log: Dependencies
Prerequisites and external inputs that can block POC or full import readiness.
Dependency ID | Phase | Dependency | Why Required | Owner | Required By | Status | Related Jira | Notes
D-001 | POC / Full | HCSC qTest licensing and permissions | HS users can share the HCSC AD identity, but still require qTest licenses and target authorization. | HCSC qTest Admin | Before POC validation / user testing | Open
D-002 | POC / Full | HS permission groups / profiles assessment | Required HS permission groups/profiles may need to be recreated in HCSC qTest. | HCSC qTest Admin / ELEKS | Before rehearsal | Open |  | Determine whether HS group/profile/permission information can be extracted by available qTest API/SCIM/admin methods.
D-003 | POC | HCSC target project and API write access | Importer requires a configured HCSC test project and credentials with create/update permissions. | HCSC qTest Admin | Before POC import | Open
D-004 | POC / Full | SharePoint migration storage and access | Approved shared storage is required for HS export packages, mappings, attachments, and logs before HCSC import. | Platform / Security | Before POC import | Open |  | Connectivity/access path has been tested; confirm operational permissions and retention.
D-005 | Full | Final Jira source-to-target mapping | External Jira references must point to the approved HCSC-side target projects; mappings may change during the project. | Jira Integration Owner | Before final migration | Open |  | Keep mapping configurable and external to migration code.

## Dashboard
qTest Consolidation — RAID Dashboard
Category | Open | In Progress | Resolved/Validated | Blocked/Escalated | Total | Primary Focus
Risks | 3 | 1 | 0 | 0 | 4 | API/version fidelity; user authorization
Assumptions | 0 | 1 | 2 | 0 | 3 | Identity reuse; SharePoint operating model
Issues | 0 | 0 | 0 | 0 | 0 | No current blocker; monitor dependencies
Dependencies | 5 | 0 | 0 | 0 | 5 | Licensing/permissions, groups, HCSC target, SharePoint, Jira
Key Project Gates
Gate | Purpose | Evidence | Owner
POC Ready | POC package, HCSC target access and required prerequisites ready | POC readiness checklist | POC Lead / HCSC
POC GO/NO-GO | Representative export/import validated and limitations accepted | POC reconciliation + demo | Client / Project Team
Rehearsal Ready | Full-scope tooling and target dependencies ready | Rehearsal readiness evidence | Project Team
Final Acceptance | Final import reconciled and accepted | Validation results + sign-off | QA / Business

## README
qTest Consolidation — RAID Log
Purpose | Concise stakeholder RAID for the HS qTest export / HCSC qTest import project.
Current status | Discovery complete; POC Export Package in progress.
Migration approach | HS qTest → export package → approved SharePoint storage → HCSC import scripts.
Connectivity | Connectivity/access required by the migration process has been tested successfully; migration is still file-mediated rather than direct qTest-to-qTest transfer.
Users | HS users are already synchronized with HCSC Active Directory; HCSC qTest licensing and permissions are still required.
Permissions | Required HS groups/profiles may need recreation in HCSC; export/API/SCIM options must be confirmed.
POC | Reduced representative scope validates export, import, mapping, relationships and reconciliation before GO/NO-GO.
Tracking | Keep only material risks/dependencies here; detailed implementation work remains in Jira/project plan.