## Gantt Progress
qTest Consolidation – Current Progress Gantt
Current status: Discovery complete • HS qTest script connectivity complete • SharePoint bridge validated • POC started • HS qTest export in progress
Planning Input | Value
Project Start | 2026-09-07
Status Date | 2026-09-16
Calendar Days
# | Activity | Status | Start | Duration | Finish | time axis 2026-09-07 to 2026-11-05
1 | Discovery & Source Assessment | Complete | 2026-09-07 | 1900-01-04 | 2026-09-11
2 | HS qTest Script Connectivity | Complete | 2026-09-07 | 1900-01-04 | 2026-09-11
3 | SharePoint Bridge Validation | Complete | 2026-09-10 | 1900-01-02 | 2026-09-12
4 | POC Export – HS qTest Information | In Progress | 2026-09-12 | 1900-01-06 | 2026-09-18
5 | POC Import & Transformation | Next | 2026-09-19 | 1900-01-09 | 2026-09-28
6 | POC Validation & Client Approval | Open | 2026-09-29 | 1900-01-04 | 2026-10-03
7 | Target Configuration & Dependencies | Open | 2026-09-16 | 1900-01-16 | 2026-10-02
8 | Full Import Tooling & Rehearsal | Open | 2026-10-04 | 1900-01-07 | 2026-10-11
9 | Final Export & Import | Open | 2026-10-12 | 1900-01-05 | 2026-10-17
10 | Final Validation & Acceptance | Open | 2026-10-18 | 1900-01-03 | 2026-10-21
Legend
Complete | Green | In Progress | Amber | Status Date | Red vertical marker
Next / Open | Light bar | Editable | Yellow cells
Note | Target Configuration & Dependencies runs in parallel with the POC.