## Migration RACI
ID | Execution Window | Method Group | Stage | Location | Activity / Control | Dependency / Why | Executed By (R) | Authorized By (A) | Consulted (C) | Informed (I) | Evidence / Exit Criteria | Jira / Risk
1 | BEFORE full migration | MANUAL - PRE | IAM plan | HCSC IAM | Agree target application-role, group and permission model with IAM. Build source→target register for logical role, App/Client ID, service principal/object ID, groups, owner and GitHub dependency. | Repo has no Okta inventory/export automation; agree logical authorization model before remapping IDs.No Okta API/client extraction exists in reviewed migration repo; IAM must export it or new automation must be built. | HCSC IAM | HCSC IAM/Security Owner | HS App Owners; GitHub Admins | Program Manager; Dev Leads | Approved target role/group model and owners documentation | New App-ID/IAM task; R-019
2 | BEFORE full migration | MANUAL - PRE | Target IAM baseline | HCSC IAM | Create/request initial HCSC groups, roles and permission structure. | Authorization structure can be prepared before final target App IDs are known. | HCSC IAM | IAM/Security Owner | ELEKS; App Owners | Program Manager | Target roles/groups exist and are ready for assignments. | DEVOPS-14690; R-019
3 | BEFORE full migration | CUSTOM SCRIPT - PRE | SCIM/team readiness | HCSC GitHub | Use GitHub SCIM/external-group tooling to create/link applicable destination teams and report mapping gaps. | Repo supports GitHub SCIM/external groups and team mapping, not Okta inventory. | ELEKS Migration Team | HCSC GitHub Admin | HCSC IAM | Repo Owners; PM | Expected groups resolve and teams are linked where supported. | DEVOPS-14690; R-008/R-019
4 | BEFORE full migration | MANUAL - PRE | Runner readiness | HCSC Zilverton | Define/create target runner groups/runners, access policies, labels, network and capacity when target org is available. | Runner resources are destination configuration; reviewed repo contains no runner migration. | HCSC Platform | HCSC Platform | Security; Network; ELEKS | Dev Leads; ELEKS | Target runner platform ready. | DEVOPS-14832
5 | BEFORE full migration | MANUAL - PRE | Gap runbooks | HCSC Zilverton | Prepare owners/runbooks for Apps, OAuth, IP allowlists, deploy keys, audit archive, webhook secrets, repo variables and environment settings. | Known non-automated/partial areas should be prepared before cutover even when final action is post-migration. | ELEKS + HCSC Admins | HCSC Admins | IAM; Security; App Owners | PM | Every manual gap has owner, prerequisite, method and validation. | DEVOPS-14839/40/44/45/46/47
6 | FULL MIGRATION RUN | GEI | Core migration | HS Zilverton → HCSC Zilverton | Run GEI organization/repository migration for supported data. | Core migration engine; production changes should be controlled because GEI has no delta migration. | ELEKS Migration Team | HCSC - HS | HCSC GitHub Admin; HS Repo Owners | IAM; Security; Dev Leads; PM | Migration results/logs captured; target repos created. | DEVOPS-14692; DEVOPS-14830
7 | FULL MIGRATION RUN | GEI | Supported repo config | HS Zilverton → HCSC Zilverton | Migrate GEI-supported metadata/configuration such as supported branch protection, Pages, autolinks and webhook data. | Custom/manual post-steps remain where GEI has limitations. | ELEKS Migration Team | HCSC | GitHub Admin | Repo Owners | GEI-supported objects present for validation. | DEVOPS-14841/42/43
8 | DURING / AFTER run | CUSTOM SCRIPT | Secrets | HS → HCSC | Migrate org, repo and environment secrets through CyberArk workflows. | Custom tooling fills GEI gaps. | ELEKS Automation | HCSC/Security Owner | CyberArk Team | Repo Owners | Expected secret configuration present and workflows validated. | DEVOPS-14830
9 | DURING / AFTER run | CUSTOM SCRIPT | Packages | HS → HCSC | Migrate container and supported package ecosystems. | Custom tooling covers containers and npm/Maven/Gradle/NuGet/RubyGems. | ELEKS Automation | HCSC | Registry Owners | Repo Owners | Required packages available from target. | DEVOPS-14830
10 | DURING / AFTER run | CUSTOM SCRIPT | Org configuration | HS → HCSC | Apply org rulesets, org Actions variables and custom properties. | Custom tooling expands org-level coverage beyond GEI. | ELEKS Automation | HCSC | Security/Governance | PM | Configuration matches approved target baseline. | DEVOPS-14831
11 | DURING / AFTER run | CUSTOM SCRIPT | Team/access reconciliation | HCSC Zilverton | Create/assign role teams, link external groups, report missing mappings and remediate repo permissions. | Existing tooling maps App-ID topics to role-based teams and reconciles access. | ELEKS Automation | HCSC / IAM Owner | HCSC IAM | Repo Owners | No unresolved critical team/SCIM/permission gaps. | DEVOPS-14692; DEVOPS-14830; R-019
12 | AFTER migration run | CUSTOM SCRIPT | Mannequin reclaim | HCSC Zilverton | Run mannequin reclamation. | Migrated placeholder identities must exist first. | ELEKS Migration Team | HCSC | HCSC IAM | Repo Owners | Required attribution reclaimed or exceptions documented. | DEVOPS-14830
13 | AFTER migration run | MANUAL - POST | App ID remap | HCSC IAM + HCSC Zilverton | Assign/recreate target application identities and map target App/Client IDs/service principals/groups to pre-created roles. | Final target identifiers/assignments are environment-specific. | HCSC IAM + App Owners | IAM/Security Owner | ELEKS | Dev Leads; PM | Mapping register has target IDs and critical assignments complete. | New App-ID/IAM task; R-019
14 | AFTER migration run | MANUAL - POST | GitHub identity references | HCSC Zilverton | Update workflow/repo/environment references containing source App IDs, tenant IDs, object IDs or other identity values. | External identity references are not made portable by repository migration. | ELEKS + App/Repo Owners | HCSC Application Owner | HCSC IAM; GitHub Admin | Dev Team | No critical configuration points to obsolete HS identifiers. | R-021/R-019
15 | AFTER migration run | MANUAL - POST | Runner binding | HCSC Zilverton | Bind target runner groups/runners to migrated repos and validate labels/groups/access. | Repository-specific access is finalized against destination repos. | HCSC Platform | Platform/GitHub Admin | ELEKS; Security | Repo Owners | Critical workflows schedule on intended target runners. | DEVOPS-14832
16 | AFTER migration run | MANUAL - POST | Repo Actions variables | HCSC Zilverton | Create/update repository Actions variables. | Known automation gap. | ELEKS / Repo Owners | Repo/GitHub Owner | App Owners | Dev Team | Required variables exist and workflows pass. | DEVOPS-14830
17 | AFTER migration run | MANUAL - POST | Environment controls | HCSC Zilverton | Recreate/verify reviewers, wait timers and deployment branch policies. | Environment secrets automated; full environment config is not. | ELEKS + Repo Owners | Repo/App Owner | Security | Dev Team | Environment controls match approved policy. | DEVOPS-14839
18 | AFTER migration run | MANUAL - POST | Webhooks | HCSC Zilverton | Re-enable required webhooks, recreate webhook secrets and test deliveries. | Webhook secrets are not migrated and destination re-enablement is required. | Integration/App Owners | Application Owner | ELEKS; GitHub Admin | Repo Owners | Successful webhook delivery confirmed. | DEVOPS-14830
19 | AFTER migration run | MANUAL - POST | Deploy keys | HCSC Zilverton | Generate/configure new deploy keys and update consumers. | Private key material is not portable. | App/Integration Owners | Application Owner | Security; ELEKS | Repo Owners | Key-based integrations authenticate. | DEVOPS-14840
20 | AFTER migration run | MANUAL - POST | GitHub Apps | HCSC Zilverton | Install/reconfigure required GitHub Apps and validate permissions/functionality. | No migration/audit automation found in reviewed repo. | GitHub Admin + App Owners | Security/GitHub Admin | ELEKS | Repo Owners | Required Apps installed and functional. | DEVOPS-14844; R-013
21 | AFTER migration run | MANUAL - POST | OAuth / IP / Audit | HCSC Zilverton | Recreate OAuth policies, configure IP allowlists and complete audit archive/target logging. | No custom coverage found for these areas. | GitHub Admin + Security/Compliance | Security/Compliance Owner | ELEKS; Network | PM | Connectivity, policy and audit controls validated. | DEVOPS-14845/46/47; R-005/R-006
22 | AFTER migration run | MANUAL - POST | Auth validation | HCSC + external platforms | Update external trust where required and validate target application authentication/authorization. | OIDC and application identity dependencies can change independently of repo migration. | App Owners + IAM + ELEKS | Application/Security Owner | Cloud Platform Owners | Dev Leads; PM | Critical applications authenticate with intended authorization. | R-021/R-019
23 | AFTER validation | MANUAL - POST | Archive / rollback | HS Zilverton | Archive source repos; if a destination repo fails, selectively unarchive its HS source so developers continue while HCSC is fixed. | Provides continuity without normal dual-write operation. | ELEKS; HCSC | Cutover Owner | Repo Owner; HCSC GitHub Admin | Developers; PM | Archive state confirmed and rollback/resync procedure documented. | DEVOPS-14848; R-015
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Antonio Machado que significa “pre”?

## Migration RACI (2)
ID | Execution Window | Method Group | Stage | Location | Activity | Description / Control | Dependency / Why | Executed By (R) | Authorized By (A) | Consulted (C) | Informed (I) | Evidence / Exit Criteria | Jira / Risk
1 | BEFORE full migration | MANUAL - PRE | IAM plan | HCSC IAM | ?? | Agree target application-role, group and permission model with IAM. Build source→target register for logical role, App/Client ID, service principal/object ID, groups, owner and GitHub dependency. | Repo has no Okta inventory/export automation; agree logical authorization model before remapping IDs.No Okta API/client extraction exists in reviewed migration repo; IAM must export it or new automation must be built. | HCSC IAM | HCSC IAM/Security Owner | HS App Owners; GitHub Admins | Program Manager; Dev Leads | Approved target role/group model and owners documentation | New App-ID/IAM task; R-019
2 | BEFORE full migration | MANUAL - PRE | Target IAM baseline | HCSC IAM |  | Create/request initial HCSC groups, roles and permission structure. | Authorization structure can be prepared before final target App IDs are known. | HCSC IAM | IAM/Security Owner | ELEKS; App Owners | Program Manager | Target roles/groups exist and are ready for assignments. | DEVOPS-14690; R-019
3 | BEFORE full migration | CUSTOM SCRIPT - PRE | SCIM/team readiness | HCSC GitHub |  | Use GitHub SCIM/external-group tooling to create/link applicable destination teams and report mapping gaps. | Repo supports GitHub SCIM/external groups and team mapping, not Okta inventory. | ELEKS Migration Team | HCSC GitHub Admin | HCSC IAM | Repo Owners; PM | Expected groups resolve and teams are linked where supported. | DEVOPS-14690; R-008/R-019
4 | BEFORE full migration | MANUAL - PRE | Runner readiness | HCSC Zilverton |  | Define/create target runner groups/runners, access policies, labels, network and capacity when target org is available. | Runner resources are destination configuration; reviewed repo contains no runner migration. | HCSC Platform | HCSC Platform | Security; Network; ELEKS | Dev Leads; ELEKS | Target runner platform ready. | DEVOPS-14832
| BEFORE full migration | MANUAL - PRE | Cross application
5 | BEFORE full migration | MANUAL - PRE | Gap runbooks | HCSC Zilverton |  | Prepare owners/runbooks for Apps, OAuth, IP allowlists, deploy keys, audit archive, webhook secrets, repo variables and environment settings. | Known non-automated/partial areas should be prepared before cutover even when final action is post-migration. | ELEKS + HCSC Admins | HCSC Admins | IAM; Security; App Owners | PM | Every manual gap has owner, prerequisite, method and validation. | DEVOPS-14839/40/44/45/46/47
6 | FULL MIGRATION RUN | GEI | Core migration | HS Zilverton → HCSC Zilverton |  | Run GEI organization/repository migration for supported data. | Core migration engine; production changes should be controlled because GEI has no delta migration. | ELEKS Migration Team | HCSC - HS | HCSC GitHub Admin; HS Repo Owners | IAM; Security; Dev Leads; PM | Migration results/logs captured; target repos created. | DEVOPS-14692; DEVOPS-14830
7 | FULL MIGRATION RUN | GEI | Supported repo config | HS Zilverton → HCSC Zilverton |  | Migrate GEI-supported metadata/configuration such as supported branch protection, Pages, autolinks and webhook data. | Custom/manual post-steps remain where GEI has limitations. | ELEKS Migration Team | HCSC | GitHub Admin | Repo Owners | GEI-supported objects present for validation. | DEVOPS-14841/42/43
8 | DURING / AFTER run | CUSTOM SCRIPT | Secrets | HS → HCSC |  | Migrate org, repo and environment secrets through CyberArk workflows. | Custom tooling fills GEI gaps. | ELEKS Automation | HCSC/Security Owner | CyberArk Team | Repo Owners | Github Action organization, repository, and environment secrets ar successfully restored from Cyberark to HCSC Zilverton. Migration resultos show no unresolved Failed/SKIPPED secrets. | DEVOPS-14830
9 | DURING / AFTER run | CUSTOM SCRIPT | Packages | HS → HCSC |  | Migrate container and supported package ecosystems. | Custom tooling covers containers and npm/Maven/Gradle/NuGet/RubyGems. | ELEKS Automation | HCSC | Registry Owners | Repo Owners | Required packages available from target. | DEVOPS-14830
10 | DURING / AFTER run | CUSTOM SCRIPT | Org configuration | HS → HCSC |  | Apply org rulesets, org Actions variables and custom properties. | Custom tooling expands org-level coverage beyond GEI. | ELEKS Automation | HCSC | Security/Governance | PM | Configuration matches approved target baseline. | DEVOPS-14831
11 | DURING / AFTER run | CUSTOM SCRIPT | Team/access reconciliation | HCSC Zilverton |  | Create/assign role teams, link external groups, report missing mappings and remediate repo permissions. | Existing tooling maps App-ID topics to role-based teams and reconciles access. | ELEKS Automation | HCSC / IAM Owner | HCSC IAM | Repo Owners | No unresolved critical team/SCIM/permission gaps. | DEVOPS-14692; DEVOPS-14830; R-019
12 | AFTER migration run | CUSTOM SCRIPT | Mannequin reclaim | HCSC Zilverton |  | Run mannequin reclamation. | Migrated placeholder identities must exist first. | ELEKS Migration Team | HCSC | HCSC IAM | Repo Owners | Required attribution reclaimed or exceptions documented. | DEVOPS-14830
13 | AFTER migration run | MANUAL - POST | App ID remap | HCSC IAM + HCSC Zilverton |  | Assign/recreate target application identities and map target App/Client IDs/service principals/groups to pre-created roles. | Final target identifiers/assignments are environment-specific. | HCSC IAM + App Owners | IAM/Security Owner | ELEKS | Dev Leads; PM | Mapping register has target IDs and critical assignments complete. | New App-ID/IAM task; R-019
14 | AFTER migration run | MANUAL - POST | GitHub identity references | HCSC Zilverton |  | Update workflow/repo/environment references containing source App IDs, tenant IDs, object IDs or other identity values. | External identity references are not made portable by repository migration. | ELEKS + App/Repo Owners | HCSC Application Owner | HCSC IAM; GitHub Admin | Dev Team | No critical configuration points to obsolete HS identifiers. | R-021/R-019
15 | AFTER migration run | MANUAL - POST | Runner binding | HCSC Zilverton |  | Bind target runner groups/runners to migrated repos and validate labels/groups/access. | Repository-specific access is finalized against destination repos. | HCSC Platform | Platform/GitHub Admin | ELEKS; Security | Repo Owners | Critical workflows schedule on intended target runners. | DEVOPS-14832
16 | AFTER migration run | MANUAL - POST | Repo Actions variables | HCSC Zilverton |  | Create/update repository Actions variables. | Known automation gap. | ELEKS / Repo Owners | Repo/GitHub Owner | App Owners | Dev Team | Required variables exist and workflows pass. | DEVOPS-14830
17 | AFTER migration run | MANUAL - POST | Environment controls | HCSC Zilverton |  | Recreate/verify reviewers, wait timers and deployment branch policies. | Environment secrets automated; full environment config is not. | ELEKS + Repo Owners | Repo/App Owner | Security | Dev Team | Environment controls match approved policy. | DEVOPS-14839
18 | AFTER migration run | MANUAL - POST | Webhooks | HCSC Zilverton |  | Re-enable required webhooks, recreate webhook secrets and test deliveries. | Webhook secrets are not migrated and destination re-enablement is required. | Integration/App Owners | Application Owner | ELEKS; GitHub Admin | Repo Owners | Successful webhook delivery confirmed. | DEVOPS-14830
19 | AFTER migration run | MANUAL - POST | Deploy keys | HCSC Zilverton |  | Generate/configure new deploy keys and update consumers. | Private key material is not portable. | App/Integration Owners | Application Owner | Security; ELEKS | Repo Owners | Key-based integrations authenticate. | DEVOPS-14840
20 | AFTER migration run | MANUAL - POST | secrets validation & Exception remedation | HCSC Zilverton |  | Validate Github Actions secrets migrated through CyberArk and remediate exceptions | Custom automation restores organization, repository, and environment Actions secrets, but failures/skips, org-secret visibility restrictions, repository mapping exceptions, and funtional availability still require post-migration validation | ELEKS + HCSC Admins | HCSC/Security Owner | cyberArk Team - Application Owners | Dev Leads; PM | Org, repo, and environment Actions secrets restores successfully from CCyberArk; Failed/Skipped items resolved;
21 | AFTER migration run | MANUAL - POST | GitHub Apps | HCSC Zilverton |  | Install/reconfigure required GitHub Apps and validate permissions/functionality. | No migration/audit automation found in reviewed repo. | GitHub Admin + App Owners | Security/GitHub Admin | ELEKS | Repo Owners | Required Apps installed and functional. | DEVOPS-14844; R-013
22 | AFTER migration run | MANUAL - POST | OAuth / IP / Audit | HCSC Zilverton |  | Recreate OAuth policies, configure IP allowlists and complete audit archive/target logging. | No custom coverage found for these areas. | GitHub Admin + Security/Compliance | Security/Compliance Owner | ELEKS; Network | PM | Connectivity, policy and audit controls validated. | DEVOPS-14845/46/47; R-005/R-006
23 | AFTER migration run | MANUAL - POST | Auth validation | HCSC + external platforms |  | Update external trust where required and validate target application authentication/authorization. | OIDC and application identity dependencies can change independently of repo migration. | App Owners + IAM + ELEKS | Application/Security Owner | Cloud Platform Owners | Dev Leads; PM | Critical applications authenticate with intended authorization. | R-021/R-019
24 | AFTER validation | MANUAL - POST | Archive / rollback | HS Zilverton |  | Archive source repos; if a destination repo fails, selectively unarchive its HS source so developers continue while HCSC is fixed. | Provides continuity without normal dual-write operation. | ELEKS; HCSC | Cutover Owner | Repo Owner; HCSC GitHub Admin | Developers; PM | Archive state confirmed and rollback/resync procedure documented. | DEVOPS-14848; R-015
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Antonio Machado que significa “pre”? Reply: @Alberto Ferrari pre significa actividades a realizar antes de ejecutar los script the migración

## Activities
ID | Activity | Description / Control | Dependency / Why | Evidence / Exit Criteria
1 | ?? | Agree target application-role, group and permission model with IAM. Build source→target register for logical role, App/Client ID, service principal/object ID, groups, owner and GitHub dependency. | Repo has no Okta inventory/export automation; agree logical authorization model before remapping IDs.No Okta API/client extraction exists in reviewed migration repo; IAM must export it or new automation must be built. | Approved target role/group model and owners documentation
2 |  | Create/request initial HCSC groups, roles and permission structure. | Authorization structure can be prepared before final target App IDs are known. | Target roles/groups exist and are ready for assignments.
3 |  | Use GitHub SCIM/external-group tooling to create/link applicable destination teams and report mapping gaps. | Repo supports GitHub SCIM/external groups and team mapping, not Okta inventory. | Expected groups resolve and teams are linked where supported.
4 |  | Define/create target runner groups/runners, access policies, labels, network and capacity when target org is available. | Runner resources are destination configuration; reviewed repo contains no runner migration. | Target runner platform ready.
5 |  | Prepare owners/runbooks for Apps, OAuth, IP allowlists, deploy keys, audit archive, webhook secrets, repo variables and environment settings. | Known non-automated/partial areas should be prepared before cutover even when final action is post-migration. | Every manual gap has owner, prerequisite, method and validation.
6 |  | Run GEI organization/repository migration for supported data. | Core migration engine; production changes should be controlled because GEI has no delta migration. | Migration results/logs captured; target repos created.
7 |  | Migrate GEI-supported metadata/configuration such as supported branch protection, Pages, autolinks and webhook data. | Custom/manual post-steps remain where GEI has limitations. | GEI-supported objects present for validation.
8 |  | Migrate org, repo and environment secrets through CyberArk workflows. | Custom tooling fills GEI gaps. | Expected secret configuration present and workflows validated.
9 |  | Migrate container and supported package ecosystems. | Custom tooling covers containers and npm/Maven/Gradle/NuGet/RubyGems. | Required packages available from target.
10 |  | Apply org rulesets, org Actions variables and custom properties. | Custom tooling expands org-level coverage beyond GEI. | Configuration matches approved target baseline.
11 |  | Create/assign role teams, link external groups, report missing mappings and remediate repo permissions. | Existing tooling maps App-ID topics to role-based teams and reconciles access. | No unresolved critical team/SCIM/permission gaps.
12 |  | Run mannequin reclamation. | Migrated placeholder identities must exist first. | Required attribution reclaimed or exceptions documented.
13 |  | Assign/recreate target application identities and map target App/Client IDs/service principals/groups to pre-created roles. | Final target identifiers/assignments are environment-specific. | Mapping register has target IDs and critical assignments complete.
14 |  | Update workflow/repo/environment references containing source App IDs, tenant IDs, object IDs or other identity values. | External identity references are not made portable by repository migration. | No critical configuration points to obsolete HS identifiers.
15 |  | Bind target runner groups/runners to migrated repos and validate labels/groups/access. | Repository-specific access is finalized against destination repos. | Critical workflows schedule on intended target runners.
16 |  | Create/update repository Actions variables. | Known automation gap. | Required variables exist and workflows pass.
17 |  | Recreate/verify reviewers, wait timers and deployment branch policies. | Environment secrets automated; full environment config is not. | Environment controls match approved policy.
18 |  | Re-enable required webhooks, recreate webhook secrets and test deliveries. | Webhook secrets are not migrated and destination re-enablement is required. | Successful webhook delivery confirmed.
19 |  | Generate/configure new deploy keys and update consumers. | Private key material is not portable. | Key-based integrations authenticate.
20 |  | Install/reconfigure required GitHub Apps and validate permissions/functionality. | No migration/audit automation found in reviewed repo. | Required Apps installed and functional.
21 |  | Recreate OAuth policies, configure IP allowlists and complete audit archive/target logging. | No custom coverage found for these areas. | Connectivity, policy and audit controls validated.
22 |  | Update external trust where required and validate target application authentication/authorization. | OIDC and application identity dependencies can change independently of repo migration. | Critical applications authenticate with intended authorization.
23 |  | Archive source repos; if a destination repo fails, selectively unarchive its HS source so developers continue while HCSC is fixed. | Provides continuity without normal dual-write operation. | Archive state confirmed and rollback/resync procedure documented.

## Governance
ID | Activity | Executed By (R) | Authorized By (A) | Consulted (C) | Informed (I)
1 | ?? | HCSC IAM | HCSC IAM/Security Owner | HS App Owners; GitHub Admins | Program Manager; Dev Leads
2 |  | HCSC IAM | IAM/Security Owner | ELEKS; App Owners | Program Manager
3 |  | ELEKS Migration Team | HCSC GitHub Admin | HCSC IAM | Repo Owners; PM
4 |  | HCSC Platform | HCSC Platform | Security; Network; ELEKS | Dev Leads; ELEKS
5 |  | ELEKS + HCSC Admins | HCSC Admins | IAM; Security; App Owners | PM
6 |  | ELEKS Migration Team | HCSC - HS | HCSC GitHub Admin; HS Repo Owners | IAM; Security; Dev Leads; PM
7 |  | ELEKS Migration Team | HCSC | GitHub Admin | Repo Owners
8 |  | ELEKS Automation | HCSC/Security Owner | CyberArk Team | Repo Owners
9 |  | ELEKS Automation | HCSC | Registry Owners | Repo Owners
10 |  | ELEKS Automation | HCSC | Security/Governance | PM
11 |  | ELEKS Automation | HCSC / IAM Owner | HCSC IAM | Repo Owners
12 |  | ELEKS Migration Team | HCSC | HCSC IAM | Repo Owners
13 |  | HCSC IAM + App Owners | IAM/Security Owner | ELEKS | Dev Leads; PM
14 |  | ELEKS + App/Repo Owners | HCSC Application Owner | HCSC IAM; GitHub Admin | Dev Team
15 |  | HCSC Platform | Platform/GitHub Admin | ELEKS; Security | Repo Owners
16 |  | ELEKS / Repo Owners | Repo/GitHub Owner | App Owners | Dev Team
17 |  | ELEKS + Repo Owners | Repo/App Owner | Security | Dev Team
18 |  | Integration/App Owners | Application Owner | ELEKS; GitHub Admin | Repo Owners
19 |  | App/Integration Owners | Application Owner | Security; ELEKS | Repo Owners
20 |  | GitHub Admin + App Owners | Security/GitHub Admin | ELEKS | Repo Owners
21 |  | GitHub Admin + Security/Compliance | Security/Compliance Owner | ELEKS; Network | PM
22 |  | App Owners + IAM + ELEKS | Application/Security Owner | Cloud Platform Owners | Dev Leads; PM
23 |  | ELEKS; HCSC | Cutover Owner | Repo Owner; HCSC GitHub Admin | Developers; PM

## Execution
ID | Activity | Execution Window | Method Group | Stage | Location
1 | ?? | BEFORE full migration | MANUAL - PRE | IAM plan | HCSC IAM
2 |  | BEFORE full migration | MANUAL - PRE | Target IAM baseline | HCSC IAM
3 |  | BEFORE full migration | CUSTOM SCRIPT - PRE | SCIM/team readiness | HCSC GitHub
4 |  | BEFORE full migration | MANUAL - PRE | Runner readiness | HCSC Zilverton
5 |  | BEFORE full migration | MANUAL - PRE | Gap runbooks | HCSC Zilverton
6 |  | FULL MIGRATION RUN | GEI | Core migration | HS Zilverton → HCSC Zilverton
7 |  | FULL MIGRATION RUN | GEI | Supported repo config | HS Zilverton → HCSC Zilverton
8 |  | DURING / AFTER run | CUSTOM SCRIPT | Secrets | HS → HCSC
9 |  | DURING / AFTER run | CUSTOM SCRIPT | Packages | HS → HCSC
10 |  | DURING / AFTER run | CUSTOM SCRIPT | Org configuration | HS → HCSC
11 |  | DURING / AFTER run | CUSTOM SCRIPT | Team/access reconciliation | HCSC Zilverton
12 |  | AFTER migration run | CUSTOM SCRIPT | Mannequin reclaim | HCSC Zilverton
13 |  | AFTER migration run | MANUAL - POST | App ID remap | HCSC IAM + HCSC Zilverton
14 |  | AFTER migration run | MANUAL - POST | GitHub identity references | HCSC Zilverton
15 |  | AFTER migration run | MANUAL - POST | Runner binding | HCSC Zilverton
16 |  | AFTER migration run | MANUAL - POST | Repo Actions variables | HCSC Zilverton
17 |  | AFTER migration run | MANUAL - POST | Environment controls | HCSC Zilverton
18 |  | AFTER migration run | MANUAL - POST | Webhooks | HCSC Zilverton
19 |  | AFTER migration run | MANUAL - POST | Deploy keys | HCSC Zilverton
20 |  | AFTER migration run | MANUAL - POST | GitHub Apps | HCSC Zilverton
21 |  | AFTER migration run | MANUAL - POST | OAuth / IP / Audit | HCSC Zilverton
22 |  | AFTER migration run | MANUAL - POST | Auth validation | HCSC + external platforms
23 |  | AFTER validation | MANUAL - POST | Archive / rollback | HS Zilverton