# qTest Consolidation

# 1. Overview

This document provides a simplified status view of the main work packages for transferring qTest information from HS qTest into HCSC qTest. It intentionally keeps the status matrix at a high level; detailed technical activities, dependencies, risks, ownership, and implementation tasks are maintained in the Technical Plan, RAID log, RACI matrix, and Jira.

# 2. Scope and Fixed Approach

The only available transfer approach is to export information from HS qTest into portable files and then import that information separately into HCSC qTest. There is no direct connectivity between the two qTest platforms.

Discovery / Assessment is a separate phase and has already produced reusable outputs through existing scripts.

Discovery outcomes are used to define the POC scope and remain inputs for later full-scope planning.

The POC validates a reduced but representative set of related qTest elements.

Jira mappings remain external and configurable because target Jira projects may change during the project.

Detailed items such as attachments, users, custom fields, relationships, execution history, API compatibility, and mappings are tracked within the relevant high-level element rather than as separate migration elements.

# 3. Status Definitions

| Status | Meaning |
| --- | --- |
| Complete | The work package has been completed and its required output/evidence is available. |
| In Progress | Work is actively underway. |
| Open | Required work has been identified but has not yet started or is awaiting readiness. |
| Blocked | Progress cannot continue until a dependency, access, approval, or technical issue is resolved. |
| TBD | A detail or decision still requires confirmation. |

# 4. Migration Elements Status Matrix

| # | Migration Element | Phase / Delivery Mode | Status | Owner | Main Dependency | Acceptance Evidence | Next Action |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Discovery & Source Assessment | Assessment / Automated | Complete | ELEKS qTest Migration Team | Existing discovery scripts and HS qTest access | Versioned inventory of qTest elements, hierarchy, relationships, configuration, and volumes. | Use discovery outcomes as the source baseline for POC scope and future planning. |
| 2 | POC Export Package | POC / Automated | In Progress | ELEKS qTest Migration Team | Discovery outcomes and approved POC scope | Representative HS qTest elements exported into validated JSON/CSV/files with source identifiers and required attachments. | Finalize the reduced POC scope and generate the controlled export package. |
| 3 | POC Import & Transformation | POC / Automated + Mapping | Open | ELEKS qTest Migration Team | HCSC test project, API access, compatibility assessment, field/user/Jira mappings | Selected qTest elements are transformed and recreated in HCSC in the required dependency order, with source-to-target ID mappings retained. | Develop and test the HCSC import and transformation scripts. |
| 4 | POC Validation & Client Approval | Validation / Automated + Manual | Open | POC Lead / QA Lead | Completed POC import | Reconciliation confirms required content, hierarchy, relationships, attachments, and mappings; limitations are documented and client GO/NO-GO is recorded. | Prepare reconciliation evidence and client POC demonstration. |
| 5 | Target Configuration & Dependencies | Readiness / Manual + External | Open | HCSC qTest Admin / Project Owners | HCSC configuration, users/permissions, secure transfer, Jira mapping, integration owners | Required HCSC configuration and external prerequisites are ready or have an approved treatment before full execution. | Resolve target readiness items and maintain dependencies in RAID/Jira. |
| 6 | Full Import Tooling & Rehearsal | Implementation / Automated + Manual | Open | ELEKS qTest Migration Team | POC GO decision, full element classification, target readiness | POC tooling is hardened for approved full scope and a representative/full rehearsal completes with acceptable timing, errors, and reconciliation. | Define full-scope element treatment, harden scripts, and execute rehearsal. |
| 7 | Final Export & Import | Final Execution / Automated + Manual | Open | ELEKS qTest Migration Team | Accepted rehearsal, final mappings, source refresh/change control, approved execution window | Final HS package is refreshed, transferred through the approved path, and imported into HCSC using the tested process. | Execute the approved final export/import runbook. |
| 8 | Final Validation & Acceptance | Validation / Acceptance | Open | QA + Business Owners | Final import complete and required integrations/mappings ready | HCSC data, hierarchy, relationships, and agreed integrations are validated; exceptions are documented and formal acceptance is obtained. | Complete reconciliation, resolve/accept exceptions, and obtain sign-off. |

# 5. What Is Included Within the High-Level Elements

| High-Level Element | Examples of Detailed Items Included |
| --- | --- |
| Discovery & Source Assessment | Projects, object inventory, hierarchy, relationships, configuration, volumes, source dependencies. |
| POC Export Package | JSON/CSV structures, attachments, source IDs, manifest, selected qTest object graph. |
| POC Import & Transformation | Requirements, test cases/steps, execution objects, ID translation, field/status mapping, users, relationships, attachments, Jira references. |
| POC Validation & Client Approval | Automated reconciliation, manual QA checks, capability/limitation matrix, POC demonstration, GO/NO-GO. |
| Target Configuration & Dependencies | HCSC project/configuration, API credentials, permissions, users, fields/statuses, secure file transfer, Jira and external integration readiness. |
| Full Import Tooling & Rehearsal | Batching, retries, checkpoints, logging, mapping configuration, full-scope handling, performance and rehearsal validation. |
| Final Export & Import | Source refresh, final package, controlled transfer, final mappings, import sequence, logs and source-to-target IDs. |
| Final Validation & Acceptance | Final reconciliation, hierarchy/relationship validation, Jira/integration checks, exception handling and sign-off. |

# 6. Lifecycle and Decision Gates

Discovery & Source Assessment → POC Export Package → POC Import & Transformation → POC Validation & Client Approval → Target Configuration & Dependencies → Full Import Tooling & Rehearsal → Final Export & Import → Final Validation & Acceptance.

The POC client review is the primary feasibility gate. A successful POC confirms the demonstrated approach for the selected scope; it does not automatically confirm that every discovered qTest element can be imported with the same fidelity. Full-scope treatment is defined after the POC using the Discovery outcomes and POC evidence.