## Risks
qTest Consolidation — RAID Log: Risks
Potential future events that could negatively affect the HS qTest export / HCSC qTest import initiative.
Risk ID | Track | Category | Risk Description | Status | Likelihood | Impact | Priority | Owner | Mitigation / Response Plan | Dependency / Trigger | Notes
R-001 | qTest | Technical | HS and HCSC qTest versions expose different API behavior or object models, causing export/import incompatibilities. | In Progress | High | High | Critical | ELEKS qTest Migration Team | Build an API capability matrix for both platforms; use a canonical migration model and test every in-scope object in the POC. | POC design / API assessment
R-002 | qTest | Technical | Some qTest elements can be exported but cannot be recreated with equivalent fidelity through the HCSC API. | In Progress | High | High | Critical | ELEKS qTest Migration Team | Use the POC to classify every selected element as Automated, Partial, Manual, Prerequisite, Unsupported, or Excluded; obtain client acceptance for limitations. | POC capability matrix
R-003 | qTest | Integration | Jira target projects or issue mappings change during the project and invalidate hard-coded migration logic. | Open | High | Medium | High | Jira Integration Owner | Keep Jira mapping external to code using mapping files; apply final mappings late and reconcile before final import. | Jira mapping workstream
R-004 | qTest | Security | Export packages contain sensitive test data or attachments and are transferred or stored without approved controls. | In Progress | Medium | High | High | Security / Compliance | Use approved storage and transfer path, least privilege, package checksums, access controls, retention rules, and cleanup procedures. | Security approval
R-007 | qTest | Identity | HS users referenced by qTest objects do not exist or cannot be uniquely mapped in HCSC. | Open | High | Medium | High | HCSC qTest Admin / IAM | Create user mapping based on approved identifiers; define handling for inactive/historical users before full import. | User mapping
R-008 | qTest | Integration | External integrations or automation continue to reference HS qTest project IDs, URLs, tokens, or object identifiers after HCSC import. | Mitigated | Medium | High | High | Integration / Automation Owners | Inventory dependencies, regenerate HCSC credentials, repoint integrations, and include functional validation in final plan. | Dependency assessment
R-009 | qTest | Operational | Source data changes after discovery and the final export package no longer matches the approved baseline. | Mitigated | High | High | Critical | HS qTest Owner | Refresh inventory/export before final execution and define a controlled change/freeze window for the final package. | Final readiness | The HS qTest is freezze prior to final migration
R-010 | qTest | Technical | Partial import leaves inconsistent HCSC data and rerunning the script creates duplicates. | Open | Medium | High | High | ELEKS qTest Migration Team | Make importer restartable/idempotent where possible; persist mapping state and validate before retrying failed batches. | Tool development
R-011 | qTest | Governance | POC success is interpreted as proof that all discovered qTest elements are production-ready for import. | Open | Medium | High | High | Project Manager / POC Lead | Use a formal POC results report and GO/NO-GO gate; clearly separate feasibility from scale/readiness. | Client POC review
R-012 | qTest | Dependency | Required HCSC permissions, test project, API credentials, or configuration approvals are not ready when POC/import testing starts. | Open | Medium | High | High | HCSC qTest Admin | Track prerequisites in dependency log with required-by dates and escalation path. | POC readiness

## Assumptions
qTest Consolidation — RAID Log: Assumptions
Planning assumptions that must be validated as the POC and full plan progress.
Assumption ID | Category | Assumption Description | Impact if Invalid | Owner | Validation Plan | Status | Date Identified | Target Validation Date | Date Validated | Notes
A-001 | Technical | HS qTest APIs allow read access to the qTest elements selected during discovery. | POC scope may need reduction or alternate export handling. | HS qTest Admin | Validate using completed discovery scripts and retain evidence. | In Progress
A-002 | Technical | HCSC qTest APIs allow creation/update of the elements selected for the POC. | POC may prove only partial feasibility. | HCSC qTest Admin | Validate API endpoints and permissions before importer development. | Open
A-003 | Architecture | No direct connectivity exists or will be used between HS and HCSC qTest; the only transfer method is export files followed by import. | Affects all tooling and operating procedures. | Project Manager | Treat file-mediated export/import as a fixed project constraint. | Validated
A-004 | Environment | A dedicated HCSC qTest test project will be available for POC imports. | POC execution blocked. | HCSC qTest Admin | Create/confirm project and required permissions. | Open
A-005 | Security | An approved mechanism exists for transferring migration packages from HS to HCSC. | Export can complete but import cannot start. | Security / Platform | Confirm approved transfer/storage mechanism and retention requirements. | Open
A-006 | Integration | Final Jira project mappings may change during the project. | Jira links cannot be hard-coded early. | Jira Owner | Use external mapping files and late binding. | Validated
A-007 | Governance | Discovery outputs remain reusable inputs for POC scope, full planning, and final reconciliation. | Rework if discovery data format is insufficient. | ELEKS qTest Migration Team | Version discovery outputs and define canonical schema. | In Progress

## Issues
qTest Consolidation — RAID Log: Issues
Current problems requiring active resolution.
Issue ID | Track | Category | Issue Description | Impact | Priority | Owner | Resolution Plan | Status | Date Raised | Target Resolution Date | Date Resolved | Notes

## Dependencies
qTest Consolidation — RAID Log: Dependencies
Prerequisites and external inputs that can block POC or full import readiness.
Dependency ID | Phase | Dependency | Why Required | Owner | Required By | Status | Related Jira | Notes
D-001 | POC | HS qTest API/service account access | Required to use discovery/export tooling and refresh selected POC data. | HS qTest Admin | Before POC package creation | Complete
D-002 | POC | HCSC qTest API/service account access | Required to create and validate objects in the HCSC test project. | HCSC qTest Admin | Before importer testing | Open
D-003 | POC | HCSC qTest test project | Isolated destination required for POC import and cleanup/retry. | HCSC qTest Admin | Before POC execution | Open
D-004 | POC | HS/HCSC qTest version and API capability matrix | Determines supported fields, endpoints, payloads, and transformation rules. | ELEKS qTest Migration Team | Before POC implementation complete | In Progress
D-005 | POC | Discovery outputs and relationship inventory | Authoritative input for POC scope and source-side reconciliation. | ELEKS qTest Migration Team | POC scope definition | Complete
D-006 | POC | Secure package transfer/storage | Needed because HS and HCSC have no direct connectivity. | Security / Platform | Before HCSC import | Open
D-007 | POC | HCSC target configuration baseline | Fields/statuses/profiles needed before related objects can be created correctly. | HCSC qTest Admin | Before import | Open
D-008 | POC | User mapping approach | Required for ownership/attribution where supported. | HCSC qTest Admin / IAM | Before user-referenced imports | Open
D-009 | Integration | Jira source-to-target mapping | Required to reconnect or preserve external references; final project may change. | Jira Integration Owner | Before final Jira reconciliation | Open
D-010 | Full Plan | Full migration element classification | Each discovered element needs final method: automated, partial, manual, prerequisite, unsupported, or excluded. | ELEKS + HCSC qTest Admin | Before rehearsal | Open
D-011 | Full Plan | HCSC Cloud | qTest HCSC Cloud should be available | HCSC qTest Admin | Before rehearsal | Open
D-012 | Full Plan | Final HCSC project/configuration readiness | Destination projects and required settings must exist before full import. | HCSC qTest Admin | Before rehearsal/final import | Open
D-013 | Full Plan | Integration and automation owner readiness | External systems may need new HCSC URLs, tokens, project IDs, and mappings. | Integration Owners | Before final validation | Open
D-014 | Final | Source refresh/freeze decision | Discovery baseline must be refreshed and final source changes controlled before final export. | HS qTest Owner / Client | Before final export | Open

## Dashboard
qTest Consolidation — RAID Dashboard
Category | Open | In Progress | Resolved/Validated | Blocked/Escalated | Total | Primary Focus
Risks | 5 | 3 | 2 | 0 | 10 | API fidelity, relationships, configuration conflicts
Assumptions | 3 | 2 | 2 | 0 | 7 | POC prerequisites and architecture constraints
Issues | 0 | 0 | 0 | 0 | 0 | Compatibility and Jira mapping gaps
Dependencies | 11 | 1 | 2 | 0 | 14 | HCSC readiness, access, transfer, client gates
Key Project Gates
Gate | Purpose | Evidence | Owner
Discovery Baseline | Inventory, hierarchy and relationships available | Versioned discovery outputs | ELEKS
POC Ready | Scope, target project, access and mappings ready | POC scope + readiness checklist | POC Lead / HCSC
POC GO/NO-GO | Client accepts feasibility and limitations | POC results + capability matrix | Client
Full Import Ready | Tooling, mappings, target config and rehearsal accepted | Readiness report | Project Team

## README
qTest Consolidation — RAID Log
Purpose | Track Risks, Assumptions, Issues and Dependencies for the HS qTest export / HCSC qTest import project.
Architecture constraint | No direct HS-to-HCSC connectivity. Information is exported to files and imported separately into HCSC.
Discovery | Separate assessment phase; existing discovery scripts and outputs are reused by the POC and later planning.
POC | Validates feasibility using a reduced, representative set of related qTest elements.
Full plan | Starts after client review and GO decision from the POC.
Status maintenance | Owners update status, dates, mitigation/resolution and evidence as Jira work progresses.
Jira mapping | External configuration because target Jira projects may change during the project.
Format | Modeled on the attached DevOps Tools Consolidation RAID workbook.