## Critical Path
qTest Consolidation - Simplified Critical Path
Configurable Input | Value |  | Edit only the Start Date in cell B4. All activity dates and the final completion date update automatically. Durations are calendar days, so weekends are included.
Start Date | 2026-09-07
Total Planned Days | 37
# | Migration Element | Main Objective | Duration (Days) | Start Date | Finish Date | Critical Path | Gate / Output
1 | Discovery & Source Assessment | Confirm and freeze the reusable Discovery baseline. | 5 | 2026-09-07 | 2026-09-11 | Yes | Discovery Baseline
2 | POC Export Package | Define POC scope and generate the controlled HS export package. | 5 | 2026-09-12 | 2026-09-16 | Yes | POC Package Ready
3 | POC Import & Transformation | Develop mappings and recreate the selected POC elements in HCSC. | 3 | 2026-09-17 | 2026-09-19 | Yes | POC Import Complete
4 | POC Validation & Client Approval | Reconcile POC results, document limitations, and obtain client GO/NO-GO. | 4 | 2026-09-20 | 2026-09-23 | Yes | POC GO / NO-GO
5 | Target Configuration & Dependencies | Close HCSC configuration, access, user, Jira, and transfer dependencies. | 7 | 2026-09-24 | 2026-09-30 | Yes | Target Ready
6 | Full Import Tooling & Rehearsal | Harden scripts for full scope and execute a focused rehearsal. | 5 | 2026-10-01 | 2026-10-05 | Yes | Rehearsal Accepted
7 | Final Export & Import | Refresh the HS package and execute the final HCSC import. | 5 | 2026-10-06 | 2026-10-10 | Yes | Final Import Complete
8 | Final Validation & Acceptance | Run final reconciliation, review exceptions, and obtain acceptance. | 3 | 2026-10-11 | 2026-10-13 | Yes | Final Acceptance
Schedule Summary |  |  | Completion date changes automatically with the Start Date. Current finish: 13-Oct-2026
Start Date | 2026-09-07
Final Completion | 2026-10-13
Total Calendar Days | 37
Formulas:
Start Date = [Finish Date, row above]+1
Finish Date = [Start Date]+[Duration (Days)]-1