Agenda august 3

- Open Actions & Blockers

  - Review actions from the previous session

  - Identify new blockers, dependencies, or decisions required

- IAM & Authorization Readiness

  - Coordination with HCSC IAM team

  - HS users accessing HCSC GitHub with their existing accounts

  - HCSC custom authorization approach

  - Access requirements, ownership, and validation

  - Open IAM decisions and dependencies

- GitHub Runners Readiness

  - Current HS self-hosted runner inventory and dependencies

  - Reuse vs. creation of runners in HCSC

  - Runner groups, labels, repository access, and security requirements

  - Network and infrastructure dependencies

  - Runner registration and cutover approach

  - Workflow validation strategy

- Decisions & Next Actions

  - Agreements reached

  - Open decisions

  - Action, owner, and target date for each pending item

Expected outcome:

Progressively close technical prerequisites and reach a clear IAM + Runners + Destination Readiness state before starting the full migration.

August 4

Agenda

- Open Actions & Blockers

  - Review actions from the previous session

  - Identify new blockers, dependencies, or decisions required

- IAM & Authorization Readiness

  - Coordination with HCSC IAM team

  - HS users accessing HCSC GitHub with their existing accounts

  - HCSC custom authorization approach

  - Access requirements, ownership, and validation

  - Open IAM decisions and dependencies

- GitHub Runners Readiness

  - Current HS self-hosted runner inventory and dependencies

  - Reuse vs. creation of runners in HCSC

  - Runner groups, labels, repository access, and security requirements

  - Network and infrastructure dependencies

  - Runner registration and cutover approach

  - Workflow validation strategy

- Decisions & Next Actions

  - Agreements reached

  - Open decisions

  - Action, owner, and target date for each pending item

Expected outcome:

Progressively close technical prerequisites and reach a clear IAM + Runners + Destination Readiness state before starting the full migration.

August 6

# Agenda

GitHub Migration – Technical Readiness Working Session

Objective: Reach agreements on the remaining pre-migration activities and assign ownership for each workstream required before the organization-to-organization migration can begin.

1. Review Open Actions

- Identify new blockers.

- APPIDs and correlation to github groups

Outcome: Updated action log with owners and target dates.

2. IAM Pre-Migration Readiness

Discussion

As agreed, IAM is not a migration workstream. HS users will continue using their existing accounts, while HCSC will implement its own authorization model for access to the destination GitHub Organization.

Topics to finalize:

- Define the HCSC authorization approach replacing the current HS APP ID model.

- Confirm how HS users will be authorized in the HCSC GitHub Organization.

- Identify any missing IAM dependencies before repository migration.

Required Outcome

- Identify the team responsible for:

- Reviewing the current IAM baseline.

- Defining the HCSC authorization model.

- Implementing the required access configuration.

- Validating user access before migration waves.

3. Runner Readiness

Discussion

Since this is an organization-to-organization migration, runner definitions can be created in advance.

The public runner definitions have already been created. The remaining work is to prepare the supporting infrastructure.

- Self-hosted Runners

- Who will install the GitHub Actions Runner software.

  - Devops Admins(Katie, Lee, Ray, Trent)

- When will be registered the runners with the HCSC Enterprise.

2. Azure Private Networking

- Who will provision the Azure Network Settings resources.

- Who will create delegated subnets.

- Who will configure routing, NSGs, DNS, firewall, and proxy.

- Who will associate the Network Settings with GitHub Runner Groups.

- Who will validate connectivity to internal resources.

- Who will certify the private runner environment is production ready.

Information Required from HS

Confirm ownership for providing:

- Self-hosted runner inventory.

- Private runner inventory.

- Repository-to-runner mappings.

- Workflow dependencies.

- Network dependencies.

- Technical support during replication.

Required Outcome

Assign an owner and expected completion date for every remaining runner-related activity.

4. Technical Dependencies

Review any remaining technical dependencies that may affect migration readiness, including:

- Secrets

# Meeting notes

These are the self-hosted runners withing the HealthSpring Domain.

Prod server

Datacenter: EWR (Piscataway New Jersey)

usmg-prod-RAES-windows-runner-01 HDCIIS0PW053.healthspring.inside (10.116.48.15)

Non-Prod Server

Datacenter: IAD (Ashburn, Virginia)

usmg-dev-RAES-windows-runner-01 HDCAPPXDW230.healthspring.inside (10.118.18.131)

I cna paste this into the Diagram - is tjhere more ray?

# Follow-up tasks

| Task | Assigned to | Due date | Bucket |
| --- | --- | --- | --- |

August 10 and 12

Agenda  13

GitHub Runners Readiness

- Current HS self-hosted runner inventory and dependencies

- Reuse HS runners in HCSC

- Runner groups, labels, repository access, and security requirements

- Network and infrastructure dependencies

- Runner registration and cutover approach

- Workflow validation strategy

- Decisions & Next Actions

  - Agreements reached

  - Open decisions

  - Action, owner, and target date for each pending item

HS Self-Hosted Runners → HCSC GitHub Connectivity Plan.docx

Agenda – Runner Readiness for Full Migration Rehearsal

Objective: Agree on the runner and networking approach for the Full Migration Rehearsal, including ownership and required maintenance windows.

- Azure Private Runners / VNet

  - Option 1 – Clone existing HS VNet: Create an equivalent VNet/private networking configuration for HCSC rehearsal. This avoids impact to current HS workloads and the validated environment could potentially be retained for final production.

  - Option 2 – Reuse current HS VNet: Temporarily disconnect/reassociate the existing private networking configuration from HS GitHub Enterprise to HCSC for rehearsal, then restore it to HS after testing.

  - Impact: Option 2 affects current HS private-runner availability and therefore requires an agreed maintenance window and rollback/restoration plan.

- Self-Hosted Runners

  - Option 1 – Clone existing runners: Create equivalent self-hosted runners for HCSC rehearsal, leaving current HS runners operational. Validated clones could potentially be retained for production.

  - Option 2 – Reuse current HS runners: During the rehearsal, stop HS workloads, deregister selected runners from HS, register them with HCSC, execute testing, then deregister from HCSC and re-register/validate them in HS.

  - Impact: Option 2 makes those runners unavailable to HS during testing and requires a maintenance window and rollback/restoration plan.

- Decision & Ownership

  - Select the approach for Private Runners and Self-Hosted Runners.

  - Confirm HCSC/HS Networking and GitHub Admin responsibilities.

  - Agree required maintenance windows, implementation dates, and runner readiness date.

Expected outcome: Agreed runner approach for the rehearsal, owners assigned, maintenance impact understood, and target readiness date established.

DevOps Tooling

DEVOPS-14952

## Private HS Runners

- Edit

- Add comment

- AssignMore

- In Progress

- Admin

Share this issue

Export

### Details

Type: Task

Resolution:Unresolved

Priority: High

Fix Version/s:

None

Affects Version/s:None

Component/s:None

Labels:

GitHubConsolidation

Project P-Code:

P00030904 - DevOps Tooling Consolidation

Application ID:

ProdEng > Build & Deploy {PRD00070205} - GitHub Enterprise {APP00006416}

Story Points:

1

Product Team:

ProdEng > Build & Deploy {PRD00070205} - GH Migrators

Last Comment:

Antonio Machado: In Github migration - open technical working session today's meeting, we discussed about whether Azure vnet private runners will be used in new Github Organization. If so, we should include HS azure networking team, otherwise, AWS self-hosted runners will be required on HCSC side. Who will make this decision? [~I327718] [~U593988]

Work Type:

Dependency

Sprint Count:

0

### Description

Click to add description

### Attachments

Options

Drop files to attach, or browse.

### Issue Links

implements

DEVOPS-14950 HS Runners: Discovery, Design, Execution

Analysis

Delete this link

Add Link

### Tempo

##### THERE ARE NO ACTIVITIES FOR YOU TO SEE FOR THIS ISSUE.

You have not recorded any activity on this issue.

Log TimePlan TimeAdd Expense

### Activity

All

Comments

Work Log

History

Activity

Transitions

Timepiece

Newest first

You can now pin up to five comments to highlight important information. Pinned comments will appear above all other comments, so they're easy to find.

Got itLearn more about pinned comments

### Collapse comment: Antonio Machado added a comment - 10/Aug/26 1:54 PM

Antonio Machado added a comment - 6 days ago

In Github migration - open technical working session today's meeting, we discussed about whether Azure vnet private runners will be used in new Github Organization. If so, we should include HS azure networking team, otherwise, AWS self-hosted runners will be required on HCSC side. Who will make this decision? Katie Prizy Alberto Ferrari

EditDeletePin

### Collapse comment: Antonio Machado added a comment - 04/Aug/26 2:34 PM

Antonio Machado added a comment - 04/Aug/26 2:34 PM

As part of the GitHub migration from the HealthSpring (HS) GitHub Enterprise to the HCSC GitHub Enterprise, we are assessing whether the existing Azure networking infrastructure used by GitHub private runners can be leveraged by the destination HCSC Enterprise.
To evaluate the feasibility and identify any required changes, could you please provide information about the current Azure networking configuration supporting the GitHub private runners?
Specifically, we are looking for:
Current Azure Infrastructure
• Azure subscription and resource group hosting the GitHub private networking resources.
• Virtual Network (VNet) name and address space.
• Subnet(s) dedicated to GitHub private runners, including CIDR ranges.
• Delegated subnet configuration used for GitHub private networking.
• Existing Microsoft.GitHub/networkSettings resource details.
• Network Security Groups (NSGs), Route Tables (UDRs), and DNS configuration associated with the runner subnet.
Connectivity
• Connectivity from the runner subnet to:
o On-premises environments
o Azure resources
o Private APIs
o Databases
o Private package repositories
o Other internal services required by GitHub Actions workflows
• Existing VPN, ExpressRoute, or VNet peering configurations supporting this connectivity.
Network Policies
• Firewall or proxy rules currently required for GitHub private runners.
• Any outbound or inbound restrictions specific to the runner subnet.
Architecture Assessment
We would also appreciate your guidance on the following:
• Can the existing Azure VNet and network connectivity be reused for the HCSC GitHub Enterprise?
• If so, would you recommend creating a new dedicated subnet and GitHub Network Settings configuration for the HCSC Enterprise while reusing the existing VNet, routing, DNS, and connectivity?
• Are there any technical or security constraints that would prevent both the HS and HCSC GitHub Enterprises from operating in parallel during the migration?
The goal is to reuse as much of the existing Azure network infrastructure as possible while preparing a separate GitHub Enterprise configuration for HCSC to support the migration with minimal disruption.
Katie Prizy

DevOps Tooling

DEVOPS-14953

## Self Hosted HS Runners

- Edit

- Add comment

- AssignMore

- In Progress

- Admin

Share this issue

Export

### Details

Type: Task

Resolution:Unresolved

Priority: High

Fix Version/s:

None

Affects Version/s:None

Component/s:None

Labels:

GitHubConsolidation

Project P-Code:

P00030904 - DevOps Tooling Consolidation

Application ID:

ProdEng > Build & Deploy {PRD00070205} - GitHub Enterprise {APP00006416}

Story Points:

1

Product Team:

ProdEng > Build & Deploy {PRD00070205} - GH Migrators

Last Comment:

Antonio Machado: In Github migration - open technical working session today's meeting, we reviewed the HS sefl-hostd runners Github connectivity plan. We completed some sections of the document, and the bullet points were approved.    Ray scheduled a follow-up meeting for next Thursday, August 13, to go deeper into the these runners network configuration.   Document updated: [ HS Self-Hosted Runners → HCSC GitHub Connectivity Plan.docx|https://myfyi.sharepoint.com/:w:/r/sites/EPMO-P00030904-DevOpsToolingConsolidation-GitHub/Shared%20Documents/GitHub%20Infra/HS%20Self-Hosted%20Runners%20%E2%86%92%20HCSC%20GitHub%20Connectivity%20Plan.docx?d=wa246892761c5422792316bd4b13efea3&csf=1&web=1&e=rMvcpZ]

Work Type:

Dependency

Sprint Count:

0

### Description

Click to add description

### Attachments

Options

Drop files to attach, or browse.

### Issue Links

implements

DEVOPS-14950 HS Runners: Discovery, Design, Execution

Analysis

Delete this link

Add Link

### Tempo

##### THERE ARE NO ACTIVITIES FOR YOU TO SEE FOR THIS ISSUE.

You have not recorded any activity on this issue.

Log TimePlan TimeAdd Expense

### Activity

All

Comments

Work Log

History

Activity

Transitions

Timepiece

Newest first

You can now pin up to five comments to highlight important information. Pinned comments will appear above all other comments, so they're easy to find.

Got itLearn more about pinned comments

### Collapse comment: Antonio Machado added a comment - 10/Aug/26 1:40 PM

Antonio Machado added a comment - 6 days ago

In Github migration - open technical working session today's meeting, we reviewed the HS sefl-hostd runners Github connectivity plan. We completed some sections of the document, and the bullet points were approved.

Ray scheduled a follow-up meeting for next Thursday, August 13, to go deeper into the these runners network configuration.

Document updated:  HS Self-Hosted Runners → HCSC GitHub Connectivity Plan.docx

EditDeletePin

### Collapse comment: Antonio Machado added a comment - 07/Aug/26 12:35 PM

Antonio Machado added a comment - 07/Aug/26 12:35 PM

Based on yesterday’s technical meeting, it was agreed that the HS Github self-hosted runners will be reused by HCSC Github and the new organization.

To make this possible, some networking configurations will be needed to properly connect these VMs to HCSC infrastructure. The HCSC and HS networking teams should discuss the best way to move forward with these activities.

I created a suggested Github connectivity plan as starting point for the discussion between both teams, based on the information we already have and what was discussed yesterday. The plan can be adjusted as new finding come up and based on the outcomes of the networking discussions.

HS Self-Hosted Runners → HCSC GitHub Connectivity Plan.docx

In addition, I created a first draft for HS to HCSC Self-hosted Runner cut over plan.

HS_to_HCSC_Self_Hosted_Runner_Cutover_Plan.docx

EditDeletePin

### Collapse comment: Alberto Ferrari added a comment - 04/Aug/26 2:30 PM

Alberto Ferrari added a comment - 04/Aug/26 2:30 PM

Katie Prizy  as per the plan this would need to be done by beginning of September.

Would you be able to deliver on time?

EditDeletePin

### Collapse comment: Antonio Machado added a comment - 03/Aug/26 10:47 AM, Edited by Antonio Machado - 04/Aug/26 2:27 PM

Antonio Machado added a comment - 03/Aug/26 10:47 AM - edited

Self-hosted Runners
Prepare the remaining self-hosted runner capability used by migrated repositories, including:
_usmg-prod-RAES-windows-runner-01
usmg-dev-RAES-windows-runner-01_
Validate runner groups (prod-raes-windows and dev-raes-windows), repository assignments, labels, and workflow compatibility before the corresponding repositories are migrated. Katie Prizy

EditDeletePin

GitHub Migration - Test Strategy Plan

- Contents

# Overview

Migration è ELEKS validaton è UAT/Prueba usuarios

This Test Strategy Plan describes quality testing activities performed by ELEKS and the HS/HCSC users on the end-to-end Test Full Migration.  Its validation is mandatory before the final production migration.

The Test Full Migration migrates the HealthSpring (HS) GitHub Production organization into a temporary organization in HCSC GitHub Enterprise Production.

The rehearsal is a full-scale production simulation: it migrates the complete HS repository list into a temporary HCSC test organization, transferring the migration-relevant HS organization and repository configuration, while applying HCSC-specific target controls where the final operating model intentionally differs from HS.

The purpose of this activity is the quality control of the migration process: validates the actual GEI (GitHub Enterprise Importer) process, custom automations, manual remediations, IAM readiness, runner/networking architecture, functional behavior, evidence collection, timing, and operational procedures before the final cutover.

# Overall Quality Test Vision

HCSC IAM coordination → HS users retain existing accounts → HCSC custom authorization model prepared → HCSC Test organization prepared → cloned runner/network infrastructure validated → full repository migration → custom/manual remediation → automated validation → HS developer testing → defect remediation → production readiness decision → final migration → functional validation → source archive

GEI process completion is an intermediate milestone, not the test exit condition. The test is only successful when the destination can be shown to operate with the intended HCSC authorization, runner, networking, secrets, package, integration, and security model.

# Test Objectives

- Migrate 100% of the in-scope HS repository inventory to the HCSC rehearsal organization.

- Exercise the same GEI workflow and migration controls intended for the final migration.

- Exercise all applicable custom migration scripts and manual post-migration procedures.

- Recreate or emulate migration-relevant HS organization/repository configuration in the HCSC test organization.

- Validate the HCSC-specific IAM and authorization model.

- Validate cloned Azure private-networking infrastructure for GitHub private runners.

- Validate cloned self-hosted runners without interrupting the existing HS production/dev runners during rehearsal.

- Gather and validate GEI, GitHub Actions, custom-script, API, and runner logs.

- Identify migration defects, permission gaps, API/rate-limit behavior, networking/security issues, configuration gaps, and manual-process weaknesses.

- Allow a controlled group of HS developers to perform functional testing against their actual migrated repositories.

- Measure execution duration and identify critical-path constraints for the production cutover.

- Update scripts, configuration, troubleshooting guidance, and the Migration Runbook based on rehearsal findings.

- Evaluate Test Exit gate.

# Non-functional tests

# Scope of the Test Full Migration

## Full repository inventory

- Repository existence, visibility, archived state and default branch.

- Git history, branches, tags, releases, pull requests and issues as supported by GEI.

- GitHub Actions workflows and reusable workflow references.

- Teams and repository access relationships.

- Rulesets and classic branch protection were applicable.

- Actions variables and custom properties.

- Environments and related controls.

- Secrets names/scopes and restoration process.

- Packages and package consumers/producers.

- Webhooks, deploy keys, GitHub Apps and external integrations.

- Runner groups, labels and workflow-to-runner dependencies.

- OIDC/external workload identity dependencies requiring target-side remediation.

## Organization configuration emulation

The HCSC temporary organization should emulate the HS migration-relevant organization state as closely as technically practical. The HS target organization will adopt the HCSC governance rules.

| Area | Rehearsal expectation |
| --- | --- |
| GEI-supported content | Migrate through the approved GEI organization-to-organization workflow. |
| Org rulesets / Actions variables / custom properties | Export from HS and apply to HCSC using the migration automation. |
| Secrets | Exercise the GitHub Rest API encryption Secret feature CyberArk-backed import/restore process; validate names, scopes and functional consumption. |
| Packages | Execute applicable package migration tooling and validate availability/consumption. |
| Repo configuration | Execute supported custom automation and record manual gaps. |
| Teams/access | Reconcile to the HCSC target authorization model; do not treat HS IAM as a migrated asset. |
| GitHub Apps / OAuth / IP / audit / webhook secrets | Exercise the defined partial/manual procedures and capture evidence. |
| OIDC / external trust | Inventory and validate target trust changes for workflows using workload identity. |

# Test Environment

## HCSC temporary organization

- Create a temporary GitHub organization inside the HCSC GitHub Enterprise.

- Apply the HCSC Enterprise policies required to make the test representative of the final target.

- Configure the organization for GEI, GitHub Actions, required Apps, security controls and auditability.

- Provide access to the migration team and the selected HS developer test group.

- Keep the rehearsal organization isolated from the final production destination so the final migration can start from a clean approved state.

- Retain logs/evidence before the temporary organization is removed or reset.

## IAM test baseline

HS users retain their existing individual accounts. HCSC prepares a custom authorization model to replace the current HS APP ID authorization approach.

- Use the HS Okta groups/members raw inventory as a baseline/reference for access requirements.

- Identify the HS users participating in rehearsal UAT and their required organization/team/repository permissions.

- Configure the HCSC-specific authorization approach for the rehearsal organization.

- Validate that users can access only the expected repositories and functions.

- Record access gaps as test defects and update the final authorization mapping.

# Runner and Networking Test Strategy

Runner validation is a mandatory part of the rehearsal because repository migration can succeed while CI/CD remains unusable. The revised strategy avoids disrupting the currently used HS runner infrastructure during rehearsal by cloning the relevant runner and networking environments.

## GitHub-hosted/public runners

The HCSC-side public/GitHub-hosted runner configurations already prepared should be reused for the rehearsal where they match the required workflow patterns.

- Validate runner groups, labels and organization access.

- Validate representative workflows that use these runners.

- Confirm capacity and policy behavior under rehearsal load.

- Record any repository-specific bindings that can only be completed after destination repositories exist.

## Azure private-networked GitHub runners

The current HS Azure private-runner networking environments will be used as the reference architecture. For the Full Migration Rehearsal, the required VNets/networking configuration will be cloned rather than detaching the currently used HS private-runner networks.

- Clone the required architecture currently represented by azure-vnet-private-networking-prod.

- Clone the required architecture currently represented by azure-vnet-private-networking-prod-V2.

- Clone the required architecture currently represented by azure-vnet-private-networking-central-us-prod.

- Create the HCSC-specific Azure/GitHub private networking configuration required by the destination Enterprise/test organization.

- Reproduce required subnet, routing, DNS, NSG, firewall, proxy and private connectivity behavior.

- Validate access from private runners to required dependencies.

- Validate all runner patterns/OS images required by the full repository inventory.

- Treat the cloned environment as a candidate final production private-runner network. If it passes rehearsal and HCSC operational/security review, retain it for final migration and production rather than rebuilding it again.

Quality decision after rehearsal: retain the cloned private-runner network for production if validated; otherwise remediate and retest before final migration.

## 6.3 Self-hosted runners

The existing HS self-hosted runners remain attached to HS during the rehearsal. Equivalent cloned runner instances will be created and registered with the HCSC rehearsal organization.

- Clone OS/version, CPU/memory profile and installed tools/SDKs needed by the workloads.

- Reproduce runner service configuration, proxy settings, certificates, DNS/network requirements and access to internal dependencies.

- Recreate required runner groups and labels in HCSC.

- Register the cloned runners to the HCSC rehearsal organization and validate Ready/Idle status.

- Execute representative workflows for each critical runner label/pattern.

- Keep current HS production/dev runners operational throughout rehearsal.

After rehearsal, two final-cutover options remain:

- Preferred where practical: retain the validated cloned self-hosted runners as the permanent HCSC runner infrastructure.

- Alternative: during final cutover, deregister selected existing HS prod/dev runners from HS and register them with HCSC, using the rehearsal clones as proof of configuration/network readiness. This alternative requires a controlled cutover and rollback procedure.

## 6.4 Current self-hosted runner examples to cover

| Runner | Runner group / labels | Rehearsal expectation |
| --- | --- | --- |
| usmg-prod-RAES-windows-runner-01 | prod-raes-windows; ssis-org-windows-production-runner; self-hosted; Windows; X64 | Clone/equivalent runner registered to HCSC and representative production-pattern workflow tested. |
| usmg-dev-RAES-windows-runner-01 | dev-raes-windows; ssis-org-windows-non-production-runner; self-hosted; Windows; X64 | Clone/equivalent runner registered to HCSC and representative non-production workflow tested. |

# Dependencies and Responsibilities

## HCSC dependencies

- Provide destination GEI credentials/permissions and required Enterprise/org administrative access.

- Implement enough of the HCSC custom authorization model to test selected HS users and repository access.

- Create/approve destination runner groups, labels and access policies.

- Provision or approve the cloned Azure VNet/private-runner networking environment.

- Provision/host cloned self-hosted runners agreed.

- Provide representative GitHub Apps/security controls/enterprise policies required for a production-like test.

- Provide GitHub Admin, IAM, Networking/Platform and Security SMEs during execution and defect review.

- Approve whether the validated cloned private-runner VNet and self-hosted runners can be retained for production.

## 7.2 HS dependencies

- Provide the complete source repository inventory/manifest and source organization access.

- Provide SSO-authorized source credentials with the scopes required by the migration tooling.

- Provide self-hosted runner inventory, groups, labels, OS/tool baseline and workload dependencies.

- Provide required internal endpoints, DNS, proxy, firewall and application connectivity requirements.

- Provide package inventory and package migration/validation requirements.

- Identify GitHub Apps, webhooks, deploy keys, OIDC and other external integration dependencies.

- Nominate representative HS developers and application/repository owners for functional testing.

- Keep current HS runners available during rehearsal and support comparison/troubleshooting.

## 7.3 Joint dependencies

- Agree the rehearsal window, freeze expectations and test communications.

- Agree the production-like HCSC policy baseline to apply to the test organization.

- Agree runner/network test cases and required internal destinations.

- Agree the HS developer UAT group and expected repository permissions.

- Agree defect severity, ownership and retest process.

- Agree evidence location and production-readiness sign-off process.

# Test Entry Criteria

- HCSC rehearsal organization created.

- Complete HS repository manifest approved.

- Source and destination GEI credentials validated.

- Migration workflow and custom scripts versioned and ready.

- Source baseline/inventory captured.

- HCSC IAM test authorization available for selected HS users.

- Public runner configuration ready where applicable.

- Cloned private-runner VNet/network configuration provisioned and connectivity prechecked.

- Cloned self-hosted runners provisioned/registered and basic connectivity prechecked.

- Required package tooling/credentials available.

- Known manual-gap runbooks have owners and validation steps.

- Logging/evidence repository/location defined.

- Rollback/cleanup approach for the rehearsal environment agreed.

# Test Execution

- Freeze and capture the HS source baseline used for comparison.

- Validate HCSC rehearsal organization, IAM access, Enterprise policies and administrative permissions.

- Validate cloned private-runner networking and cloned self-hosted runners before migration.

- Execute the full GEI organization-to-organization migration for the complete repository list.

- Capture GEI migration IDs, workflow run IDs, logs, warnings, failures, duration and retry behavior.

- Execute organization-asset replay for rulesets, Actions variables and custom properties.

- Execute secrets migration process.

- Execute package migration tooling for applicable ecosystems.

- Execute repository-level custom automation and documented manual remediation.

- Reconcile teams/access using the HCSC target authorization model.

- Perform required GitHub App, webhook, deploy-key, environment, OAuth/IP/audit and OIDC remediation/testing.

- Run automated source-vs-target validation across the full repository inventory.

- Execute representative GitHub Actions workflows across all critical runner/label/network patterns.

- Open the rehearsal organization to the selected HS developer test group.

- Execute developer functional/UAT test cases.

- Review logs and defects jointly with HCSC/HS SMEs.

- Fix scripts/configuration/runbook steps and retest failed scenarios.

- Produce the final rehearsal report and production readiness decision.

# 10. Validation Model

## 10.1 100% migration accounting

Every in-scope repository must receive a recorded result.

| Control | Expected result | Evidence |
| --- | --- | --- |
| Repository migration status | 100% of in-scope repos accounted for as pass/fail/exception | GEI logs + migration report |
| Destination repository existence | Expected target repositories exist | API inventory/diff |
| Default branch / branches / tags | Matches expected source state | Automated validation output |
| PRs/issues/history | GEI-supported history preserved | Automated counts + deep sample |
| Org/repo configuration | Expected automated/manual state present | Config reconciliation report |
| Secrets | Expected names/scopes restored; functional consumers work | Secrets report + workflow test |
| Packages | Required packages/versions accessible | Package validation evidence |
| Teams/access | HCSC target authorization behaves as designed | Access reconciliation + UAT |
| Runner dependencies | All critical runner patterns validated | Workflow run evidence |

## 10.2 Deep risk-based validation

- Large/complex repositories, including known outliers.

- Repositories with high branch/tag/PR/issue volume.

- Business-critical applications.

- Each distinct runner label/group pattern.

- Private-network-dependent workflows.

- Self-hosted-runner workflows.

- Workflows consuming secrets or packages.

- Environment approvals/protection rules.

- Cross-repository reusable workflows/actions.

- GitHub Apps/webhooks/deploy keys.

- OIDC or service-principal authentication.

- Repositories with known manual migration gaps.

# HS Developer Functional Test

A controlled group of HS developers should test the HCSC rehearsal organization after technical validation. They should use actual migrated repositories relevant to their work.

- Authenticate and access the HCSC rehearsal organization with existing individual accounts.

- Confirm expected repository visibility and permissions.

- Clone/fetch a migrated repository.

- Create a test branch, commit and push.

- Create and review a pull request where permitted.

- Trigger representative GitHub Actions workflows.

- Confirm the expected runner group/label is selected.

- Confirm private-network workflows reach required internal services.

- Confirm workflows can consume restored test secrets and required packages.

- Validate reusable workflow/action references.

- Validate environment approvals and deployment controls where applicable.

- Validate representative external integrations/authentication.

- Record PASS/FAIL, evidence and comments for each test.

# Logging and Evidence

- GitHub Actions workflow run IDs and logs.

- GEI migration IDs and logs.

- Source and destination repository inventory snapshots.

- Custom-script logs for secrets, packages and configuration.

- GitHub API warnings/errors and rate-limit events.

- Runner registration/readiness and workflow scheduling evidence.

- Private-network connectivity test evidence.

- IAM/access reconciliation evidence.

- HS developer UAT results.

- Manual remediation checklist and operator evidence.

- Defect records, root-cause notes, fixes and retest evidence.

- Execution duration by major stage.

- Final source-vs-target reconciliation report.

# Defect Management and Retest

| Severity | Definition | Effect |
| --- | --- | --- |
| Critical | Data loss, systemic access/security failure, or condition that makes final migration unsafe. | Blocks readiness. |
| High | Critical workload/repository/runner/integration unusable without acceptable workaround. | Blocks affected scope unless formally accepted. |
| Medium | Non-critical issue with workaround and owned remediation. | May proceed with condition. |
| Low | Minor/cosmetic/non-operational issue. | Does not block readiness. |

Each defect should record repository/application, test step, expected result, actual result, log/evidence reference, severity, owner, root cause, corrective action, retest result and final status.

# Known Failure Scenarios to Exercise/Observe

- GEI incomplete/missing repository behavior and safe rerun.

- Large repository/archive timeout behavior.

- API rate limiting / HTTP 502-503 retry behavior.

- Proxy/network failures to GitHub or migration archive endpoints.

- Expired/incorrect PAT scopes or SSO authorization.

- Ruleset/variable/custom-property replay warnings or conflicts.

- Missing destination secrets before CyberArk restoration.

- Runner label mismatch or unavailable runner.

- Private runner unable to reach internal dependency.

- Cross-org workflow reference still pointing to HS.

- OIDC subject/trust mismatch after org name changes.

# Exit Gate

## Exit Gate criteria

- 100% of in-scope repositories have a migration result and evidence.

- No unresolved Critical migration/data-integrity defect.

- All High defects are resolved/retested or explicitly accepted with owner and production action.

- Applicable custom scripts are completed, and their failures/exceptions are understood.

- HCSC target IAM/access works for the selected HS developer group.

- All critical runner patterns are validated, including cloned self-hosted and private-networked runners.

- Required private connectivity is proven from the cloned HCSC private-runner environment.

- Representative critical workflows are executed successfully.

- Critical secrets/packages/integrations used by tested workloads operate in HCSC.

- Developer UAT is completed with recorded results.

- Migration timing and operational constraints are understood.

- Runbook/script changes from rehearsal findings are completed or tracked.

- The Evidence package is complete.

- A production runner decision is made retain cloned infrastructure or transition selected current HS runners at final cutover.

- A formal READY, READY WITH CONDITIONS, or NOT READY decision is recorded.

## Exit Gate evaluation

The activity concludes with one of three outcomes:

- READY — no blocking quality issue remains and the production process is understood and repeatable.

- READY WITH CONDITIONS — no Critical blocker remains, but defined non-blocking actions must be completed before or during final migration.

- NOT READY — one or more blocking conditions require remediation and targeted or full retest.

# Test Migration Deliverables

- Full Migration Test Report.

- Complete repository migration status/reconciliation report.

- Migration Evidence Package.

- Runner and networking validation report.

- HS Developer UAT results.

- Defect/exception register with ownership and retest status.

- Updated migration scripts/configuration where required.

- Updated Migration Runbook and troubleshooting guidance.

- Rehearsal-to-Production Delta Register.

- Production runner/network architecture decision.

- Production Migration Readiness recommendation.

# Critical Path for the Rehearsal

Complete HS inventory → HCSC rehearsal organization → HCSC IAM test authorization → cloned private VNet + cloned self-hosted runners → connectivity validation → full GEI migration → custom/manual configuration → automated reconciliation → runner/workflow validation → HS developer UAT → defect remediation/retest → production readiness → final migration