## Slide 1
DevOps Tools Consolidation program
GitHub Migration Overall Guide
eleks
HCSC
GitHub Migration Overall Guide
Overall Life Cycle
Identity and authorization readiness precede repository migration; remediation and functional validation follow before the HS source environment is archived.
1
HCSC IAM Coordination
Coordinate with HCSC IAM to define and prepare the destination authorization model.
→
2
HS Users Retain Existing Accounts
HS users continue to use their current individual accounts.
→
3
HCSC Custom Authorization Model
Define and validate the HCSC-specific authorization approach for HS users.
→
4
Destination Access Configured / Validated
Validate that required HS users have the necessary HCSC GitHub access.
→
5
Repository Migration
Migrate repositories and supported configuration using GEI and automation.
→
6
Post-Migration Remediation
Restore gaps: secrets, runners, variables, integrations, security and access.
→
7
Functional Validation
Validate workflows, authentication, security, integrations and application functionality.
→
8
Source Archive
Archive validated HS sources and retain selective rollback if required.
Key Principles
IAM is pre-migration readiness; HS accounts are retained.
HCSC authorization replaces the HS APP ID approach.
GEI completion is an intermediate milestone, not the exit condition.
Validation covers secrets, runners, packages, integrations and authorization.
Successful validation precedes HS source archive.
Dependency Chain (Critical Path)
IAM
→
Accounts
→
Authorization
→
Access
→
Migration
→
Remediation
→
Validation
→
Archive