# GitHub Migration Overall Guide

## Overall Life Cycle.

The migration should be understood as an end-to-end transition in which identity and authorization readiness precede repository migration, and repository migration is followed by remediation and business/technical validation before the HS source environment can be archived.

HCSC IAM coordination → HS users retain existing accounts → HCSC custom authorization model prepared → destination access configured/validated → repository migration → post-migration remediation → functional validation → source archive

This path represents the overall migration lifecycle and the principal dependency chain. IAM activities at the beginning of the path are pre-migration coordination and authorization readiness activities, not an IAM or user-account migration. HS users retain their existing accounts, while HCSC establishes the custom authorization approach required for those users to operate in the destination GitHub Organization.

The repository migration itself is therefore one stage within a broader transition. Successful completion requires the destination access model to be ready before cutover and the required post-migration configuration, integrations, security controls, and application functionality to be validated before the source organization is archived.

### IAM dependency on the critical path

IAM remains on the logical critical path as a pre-migration readiness dependency only. There is no IAM migration activity.

The corrected dependency chain is:

HCSC IAM coordination → HS existing-account access readiness → HCSC custom authorization readiness → destination access configuration → repository migration and post-migration remediation → functional validation → source archive

This means repository cutover readiness depends on the destination authorization model being prepared and validated, rather than on migrating HS identities or reproducing the HS APP ID model.

## IAM and User Authorization Approach

IAM is not a migration workstream for this GitHub consolidation. No HS user identities or accounts are migrated into HCSC as part of the GitHub migration.

As a pre-migration prerequisite, the migration team works with the HCSC IAM team to define, prepare, and validate the destination access and authorization model before repository cutover.

### User identities

Existing HS users will continue to use their current individual accounts to access the HCSC GitHub Organization. The migration does not include creation, conversion, or migration of HS user accounts.

The objective is to confirm before cutover that the required HS users can access the HCSC GitHub Organization with their existing accounts and can receive the authorization required for migrated repositories and applications.

### APP ID authorization strategy

The APP ID strategy currently used in HS is not migrated or reproduced as-is in HCSC.

HCSC will use a custom HCSC authorization approach to manage authorization for HS users within the HCSC GitHub Organization. This destination approach replaces any assumption that HS APP IDs are transferred or directly mapped during migration.

Pre-migration activities with the HCSC IAM team include:

Identify HS users and their destination access requirements.

Confirm that HS users will use their existing individual accounts.

Define the HCSC-specific authorization approach replacing the HS APP ID model.

Determine how required organization, team, repository, and application permissions will be granted in HCSC.

Validate destination authorization before the affected repositories and applications are approved for cutover.

Document and remediate authorization exceptions or access gaps.

### HCSC IAM authorization readiness gate

IAM is therefore a cutover readiness dependency, not a migration stage.

The readiness gate is satisfied when the HCSC IAM team and migration stakeholders confirm that required HS users can use their existing accounts and that the HCSC-specific authorization model is ready to provide the required destination GitHub access.

## 1. Summary

The migration is a coordinated platform, identity, repository, automation, security, and application cutover, not only a GitHub repository copy.

The overall approach has five operational phases:

Prepare the destination and manual gap runbooks before production migration.

Run GitHub Enterprise Importer (GEI) to move the core organization/repository content and supported configuration.

Run custom automation to restore capabilities not fully covered by GEI, including secrets, packages, organization configuration, and access reconciliation.

Complete manual post-migration remediation for identity references, runners, variables, environments, integrations, GitHub Apps, OAuth/IP/audit controls, and authentication.

Validate the destination and archive the source, keeping selective rollback available for repositories that fail validation.

The most important concept is that GEI completion is an intermediate milestone, not the migration exit condition. The migration should be considered operationally complete only after critical workloads can authenticate, obtain secrets, schedule on runners, access packages, satisfy environment controls, invoke integrations, and operate with the intended HCSC authorization model.

## 2. Migration Scope and Operating Model

### Source and destination

Source organization: HS Zilverton

Destination organization: HCSC Zilverton

Destination IAM: HCSC IAM

Supporting platforms: CyberArk, package registries, external/cloud platforms, GitHub SCIM/external groups, runner infrastructure

### Migration mechanisms

| Mechanism | Purpose | Typical timing |
| --- | --- | --- |
| Manual - Pre | Prepare target IAM, runners, ownership and runbooks | Before full migration |
| Custom Script - Pre | Prepare SCIM/external-group and team relationships | Before full migration |
| GEI | Migrate core repositories and supported GitHub metadata/configuration | Full migration run |
| Custom Script | Fill GEI coverage gaps: secrets, packages, org config, access reconciliation, mannequins | During/after GEI |
| Manual - Post | Rebuild non-portable or environment-specific configuration and validate applications | After migration |

### Primary stakeholder groups

ELEKS Migration Team / ELEKS Automation — migration execution and automation

HCSC GitHub Admin — destination GitHub administration and authorization

HCSC IAM — identities, groups, roles, App IDs and service principals

HCSC Platform — target runners and platform connectivity

Security / Compliance / Network — controls, IP policies, audit, access and network requirements

Application / Integration / Repository Owners — application-specific configuration and validation

CyberArk Team — secret relay/restoration support

Program / Cutover Owners — governance, communications, cutover decision and source archive

## 3. End-to-End Migration Flow

flowchart TD
    A[1. IAM model and target baseline] --> B[2. SCIM/team readiness]
    A --> C[3. Runner readiness]
    A --> D[4. Manual gap runbooks]
    B --> E[5. GEI core migration]
    C --> E
    D --> E

    E --> F[6. GEI-supported repo configuration]
    E --> G[7. Restore secrets via CyberArk]
    E --> H[8. Migrate packages]
    E --> I[9. Apply org configuration]
    E --> J[10. Reconcile teams and permissions]

    J --> K[11. App ID remap]
    K --> L[12. Update GitHub identity references]
    C --> M[13. Bind target runners]
    G --> N[14. Validate secrets and remediate exceptions]

    F --> O[15. Rebuild repo/environment/integration settings]
    L --> P[16. Application authentication validation]
    M --> P
    N --> P
    H --> P
    O --> P

    E --> Q[Mannequin reclaim]
    P --> R[17. Cutover validation]
    Q --> R
    R --> S[18. Archive HS source / selective rollback if needed]

The diagram shows the main blocking sequence. Several post-migration activities can be executed in parallel once destination repositories exist.

# 4. Phase 1 — Pre-Migration Readiness

The goal of the pre-migration phase is to ensure the HCSC destination is capable of accepting migrated repositories without creating a large uncontrolled outage window.

## 4.1 IAM plan

Owner: HCSC IAM

Accountable: HCSC IAM / Security Owner

Consulted: HS App Owners, GitHub Admins

### Activity

Agree the target application-role, group and permission model. Build a source-to-target register that includes:

logical application role

App/Client ID

service principal/object ID

groups

owner

GitHub dependency

### Dependency

The reviewed migration automation does not provide an Okta inventory/export mechanism. Identity and authorization data must therefore be supplied by IAM or by separately built automation.

### Exit criterion

An approved target role/group model and ownership mapping exists.

### Why it matters

This is a foundational dependency for SCIM/team reconciliation and post-migration App ID remapping. A repository can migrate successfully while its workflows and applications still fail because identity values belong to the source tenant/application model.

## 4.2 Target IAM baseline

Owner: HCSC IAM

Create the initial HCSC groups, roles and permission structure before final target application IDs are necessarily known.

Exit criterion: target roles/groups exist and are ready for assignments.

This work can begin early and should not be deferred until after repositories are migrated.

## 4.3 SCIM and team readiness

Owner: ELEKS Migration Team

Accountable: HCSC GitHub Admin

Dependency: target IAM/group model

Use GitHub SCIM/external-group tooling to create or link destination teams and report mapping gaps.

The tooling covers GitHub SCIM/external groups and team mapping, but does not replace the source identity-system inventory.

Exit criterion: expected groups resolve, destination teams exist where required, and external-group links are established where supported.

## 4.4 Runner readiness

Owner: HCSC Platform

Prepare the target runner platform:

runner groups

runners

access policies

labels

network connectivity

capacity

The workbook explicitly identifies runner migration as a gap: runner resources are destination configuration and are not migrated by the reviewed repository tooling.

Exit criterion: target runner platform is ready before production cutover.

Repository-specific runner binding may still need to occur after the destination repositories exist.

## 4.5 Manual gap runbooks

Owners: ELEKS + HCSC Admins

Before the cutover, prepare owner-specific runbooks for known manual/partial gaps:

GitHub Apps

OAuth policies

IP allowlists

deploy keys

audit archive/target logging

webhook secrets

repository Actions variables

environment configuration

Exit criterion: every manual gap has an owner, prerequisite, method and validation step.

This activity reduces the post-GEI cutover window because the team should already know exactly what must be rebuilt and who performs it.

## Phase 1 readiness gate

Do not enter the production migration window until, at minimum:

IAM model is approved.

Destination role/group baseline exists.

Critical SCIM/team mappings are understood.

Target runners are provisioned and reachable.

Manual gap runbooks and owners are defined.

Required HCSC GitHub and IAM administrative access is confirmed.

# 5. Phase 2 — Full Migration Run with GEI

## 5.1 Core migration

Method: GitHub Enterprise Importer (GEI)

Owner: ELEKS Migration Team

Location: HS Zilverton → HCSC Zilverton

GEI performs the supported organization/repository migration and creates the destination repositories.

### Critical operational constraint

The workbook states that GEI has no delta migration. This means the production cutover must be tightly controlled because continuing source changes after the migration snapshot can create divergence.

### Exit criterion

migration results/logs captured

target repositories created

migration failures identified for remediation

## 5.2 GEI-supported repository configuration

GEI also migrates supported metadata/configuration such as:

supported branch protection

Pages

autolinks

webhook data where supported

This should not be interpreted as complete GitHub configuration parity. The workbook explicitly calls out multiple custom and manual post-migration areas.

Exit criterion: GEI-supported objects are present and available for validation.

# 6. Phase 3 — Custom Automation After Core Migration

Once the destination repositories exist, several remediation streams can begin in parallel.

## 6.1 Secrets migration through CyberArk

Owner: ELEKS Automation

Accountable: HCSC / Security Owner

Consulted: CyberArk Team

Migrate GitHub Actions secrets at:

organization level

repository level

environment level

The custom process uses CyberArk to fill a GEI gap.

### Exit criterion

organization, repository and environment secrets are restored to HCSC Zilverton

migration results contain no unresolved FAILED or SKIPPED critical secrets

functional workflows can retrieve the required secrets

### Important distinction

The automated restoration activity and the manual validation activity are separate. Automation may complete while exceptions still exist because of visibility restrictions, repository mapping issues or downstream workflow behavior.

## 6.2 Packages

Owner: ELEKS Automation

Migrate supported package ecosystems, including the workbook-listed coverage for:

containers

npm

Maven

Gradle

NuGet

RubyGems

Exit criterion: required packages are available from the target environment.

Package availability is an application/workflow dependency and therefore should be validated before declaring a workload operational.

## 6.3 Organization configuration

Apply destination organization configuration such as:

organization rulesets

organization Actions variables

custom properties

Exit criterion: destination organization configuration matches the approved HCSC baseline.

## 6.4 Team and access reconciliation

Owner: ELEKS Automation

Accountable: HCSC / IAM Owner

Create/assign role teams, link external groups, report missing mappings and remediate repository permissions.

The workbook notes that existing tooling maps App-ID topics to role-based teams and reconciles access.

Exit criterion: no unresolved critical team, SCIM or repository-permission gaps.

This is a major dependency for restoring normal user and application access.

## 6.5 Mannequin reclamation

Owner: ELEKS Migration Team

Run mannequin reclamation after migrated placeholder identities exist.

Exit criterion: required attribution is reclaimed or documented as an accepted exception.

This is important for repository history/ownership integrity, but for many applications it is less likely to be the main service-restoration blocker than secrets, IAM, runners or authentication.

# 7. Phase 4 — Manual Post-Migration Remediation

These activities exist because some configuration is environment-specific, contains non-portable credentials/IDs, or is not covered by GEI/custom scripts.

## 7.1 App ID remap

Owners: HCSC IAM + App Owners

Assign/recreate target application identities and map target:

App/Client IDs

service principals

groups

role assignments

against the pre-created target authorization model.

Dependency: target identity baseline exists and destination application context is known.

Exit criterion: mapping register contains target IDs and all critical assignments are complete.

## 7.2 Update GitHub identity references

Owners: ELEKS + App/Repo Owners

Update workflows, repositories and environments that still reference source-specific values such as:

App IDs

tenant IDs

object IDs

service principal IDs

other identity/trust values

Exit criterion: no critical configuration points to obsolete HS identifiers.

This follows App ID remapping because the new values must exist before references can be updated reliably.

## 7.3 Runner binding

Owner: HCSC Platform

Bind the prepared runner groups/runners to the migrated repositories and verify:

labels

runner group access

repository access

scheduling

Exit criterion: critical workflows schedule on the intended HCSC runners.

This activity depends on both pre-created runner infrastructure and migrated destination repositories.

## 7.4 Repository Actions variables

Create/update repository-level Actions variables that are not covered by the existing automation.

Exit criterion: required variables exist and dependent workflows pass.

## 7.5 Environment controls

Recreate or verify:

required reviewers

wait timers

deployment branch policies

Environment secrets are automated, but the full environment configuration is not.

Exit criterion: destination environment controls match approved policy.

## 7.6 Webhooks

Re-enable required webhooks, recreate webhook secrets and test delivery.

Dependency: webhook secrets are not migrated, and destination webhooks may require explicit re-enablement.

Exit criterion: successful webhook delivery is confirmed.

## 7.7 Deploy keys

Generate/configure new deploy keys and update consumers.

Private key material is not portable and therefore should not be treated as migrated content.

Exit criterion: key-based integrations authenticate successfully.

## 7.8 Secrets validation and exception remediation

After automated CyberArk restoration:

validate org/repo/environment secret presence

review FAILED/SKIPPED results

resolve org-secret visibility restrictions

resolve repository mapping exceptions

perform functional workflow validation

Exit criterion: critical secrets are restored and exceptions are resolved or formally accepted.

## 7.9 GitHub Apps

Install/reconfigure required GitHub Apps and validate permissions and functionality.

The workbook states that no migration/audit automation was found for this area.

Exit criterion: required GitHub Apps are installed in HCSC and functional.

## 7.10 OAuth, IP allowlists and audit

Owners: GitHub Admin + Security/Compliance

Recreate or configure:

OAuth policies

IP allowlists

audit archive

target audit logging

Exit criterion: connectivity, policy and audit controls are validated.

These controls can block users, runners, applications or integrations even when repository migration itself succeeded.

## 7.11 End-to-end authentication validation

Owners: App Owners + IAM + ELEKS

Update external trust where required and validate application authentication/authorization against HCSC.

The workbook explicitly warns that OIDC and application identity dependencies can change independently of repository migration.

Exit criterion: critical applications authenticate with the intended authorization.

This is one of the strongest business-service exit gates in the plan.

# 8. Phase 5 — Validation, Cutover Completion and Source Archive

## 8.1 Overall validation gate

Before archiving HS Zilverton, validate at least the following for critical repositories/applications:

| Area | Required validation |
| --- | --- |
| Repository migration | Target repository exists and expected content/config is present |
| Access | Critical teams/users have intended permissions |
| Identity | Target App IDs/service principals/groups are assigned |
| Secrets | Required org/repo/environment secrets are usable |
| Packages | Required artifacts are available from target |
| Runners | Workflows schedule on correct runners |
| Actions variables | Required repository variables exist |
| Environments | Reviewers/timers/branch policies are correct |
| Webhooks | Required deliveries succeed |
| Deploy keys | Key-based integrations authenticate |
| GitHub Apps | Required Apps are installed and authorized |
| OAuth/IP | Policies allow intended connectivity and block unintended access |
| Audit | Required logs/archive controls are operating |
| Application auth | Critical applications authenticate and authorize correctly |
| Attribution | Required mannequins reclaimed or exceptions recorded |

## 8.2 Archive and rollback model

Location: HS Zilverton

Owner: ELEKS + HCSC

Accountable: Cutover Owner

After validation, archive the source repositories.

The workbook proposes a selective rollback/continuity model:

The normal state is not dual-write.

If a destination repository fails, its HS source can be selectively unarchived so developers can continue working while HCSC is repaired.

The rollback/resynchronization method should be documented because GEI does not provide a normal delta-migration model.

Exit criterion: source archive state is confirmed and the rollback/resync procedure is documented.

# 9. Dependency Model

## Foundational dependencies

### IAM model → access and application identity

The HCSC authorization model must be agreed before final access reconciliation and App ID mapping can be completed.

### Target repositories → repository-specific remediation

Runner binding, repo variables, environment settings, webhook activation, repository permissions and many application-specific fixes require the destination repositories to exist.

### Target App IDs → GitHub identity-reference updates

Source identity references cannot be replaced until target application identities/service principals are created or assigned.

### Secret restoration → functional workflow validation

A workflow can exist and have runner access but still fail until its required secrets are available.

### Runner platform → workflow execution

Critical workflows cannot be validated without usable target runners and correct repository binding.

### Packages → build/deployment success

Migrated code may depend on package/container artifacts that must be accessible in HCSC.

### Manual integration controls → external connectivity

Webhooks, deploy keys, Apps, OAuth policies, IP allowlists and external trust often require explicit reconfiguration.

### Application validation → source archive

Source repositories should not be archived until critical workloads have passed destination validation.

# 10. Inferred Critical Path

Because the workbook has no effort/duration data, the critical path below represents the logical blocking path to operational cutover, not a calculated schedule critical path.

## Critical path sequence

1. IAM plan

→ 2. Target IAM baseline

→ 3. SCIM/team readiness

→ 4. Runner readiness + manual gap runbooks

→ 5. GEI core migration / target repo creation

→ 6. Team/access reconciliation

→ 7. App ID remap

→ 8. Update GitHub identity references

→ 9. Secrets restoration + exception remediation

→ 10. Runner binding

→ 11. Environment/repo/integration remediation needed by critical workloads

→ 12. End-to-end application authentication/workflow validation

→ 13. Source archive / cutover completion

## Why these activities are critical

They form the minimum chain needed to move from “repository copied” to “application operational in HCSC.” A delay in any of these areas can prevent production workloads from working even if GEI reports a successful migration.

### High-risk critical dependencies

IAM / App ID availability — blocks access and identity reference remediation.

GEI production run — creates the target repositories required by downstream repository-specific work.

Secrets — missing or skipped secrets can stop Actions and deployments.

Runners — workflows cannot run if target runner access/labels/network are wrong.

External trust and identity references — OIDC/application authentication may fail after tenant/App ID changes.

Manual integration gaps — webhooks, deploy keys and GitHub Apps can silently break downstream systems.

Validation before archive — archiving too early removes the most direct continuity fallback.

# 11. Activities That Can Run in Parallel

Parallelizing the following work reduces the cutover duration.

## Before GEI

Once the IAM direction is agreed, these can largely proceed in parallel:

target IAM baseline creation

runner provisioning and network validation

gap runbook preparation

SCIM/team readiness

collection of App IDs, integration owners and repo-specific dependencies

## After target repositories exist

These streams can usually proceed concurrently, subject to repo/application dependencies:

secrets restoration

package migration

organization configuration

team/access reconciliation

mannequin reclamation

runner binding

repository Actions variables

environment controls

webhook configuration

deploy key replacement

GitHub App installation

OAuth/IP/audit configuration

The final convergence point is functional validation of critical applications and workflows.

# 12. Recommended Cutover Gates

## Gate A — Ready for production migration

Proceed only when:

IAM design is approved.

target groups/roles exist.

required admin permissions are verified.

runner infrastructure is ready.

SCIM/team mapping is understood.

manual gap runbooks have named owners.

rollback ownership and communication path are agreed.

## Gate B — GEI migration accepted

Proceed to restoration/remediation when:

target repos were created.

GEI logs/results were captured.

failed repositories are identified.

supported repository configuration is available for validation.

## Gate C — Platform and access restored

Require:

critical teams/permissions reconciled.

required secrets restored with no unresolved critical FAILED/SKIPPED results.

packages available.

runners bound and able to schedule critical workflows.

required repo variables/environment controls restored.

## Gate D — Application/integration validation passed

Require:

target App IDs/service principals mapped.

source identity references replaced.

webhooks/deploy keys/GitHub Apps restored where required.

OAuth/IP controls allow intended operations.

critical workflows and applications authenticate and execute successfully.

## Gate E — Cutover complete

Only after Gate D:

archive HS source repositories.

preserve documented selective unarchive/rollback process.

record accepted exceptions and owners.

# 13. RACI Summary by Phase

| Phase | Primary Responsible | Key Accountable / Authority | Main Consulted Parties |
| --- | --- | --- | --- |
| IAM preparation | HCSC IAM | IAM/Security Owner | App Owners, GitHub Admins, ELEKS |
| SCIM/team readiness | ELEKS Migration Team | HCSC GitHub Admin | HCSC IAM |
| Runner readiness | HCSC Platform | Platform leadership/admin | Security, Network, ELEKS |
| GEI migration | ELEKS Migration Team | HCSC / HS cutover authorities | GitHub Admin, Repo Owners |
| Secrets/packages/org config | ELEKS Automation | HCSC / Security / Governance | CyberArk, Registry Owners, Repo Owners |
| Access reconciliation | ELEKS Automation | HCSC / IAM Owner | HCSC IAM, Repo Owners |
| App identity remap | HCSC IAM + App Owners | IAM/Security Owner | ELEKS |
| Repo/environment remediation | ELEKS + Repo/App Owners | Repo/Application Owners | Security, IAM, GitHub Admin |
| Integrations | App/Integration Owners | Application Owners | ELEKS, Security, GitHub Admin |
| OAuth/IP/Audit | GitHub Admin + Security/Compliance | Security/Compliance Owner | Network, ELEKS |
| App auth validation | App Owners + IAM + ELEKS | Application/Security Owner | Cloud Platform Owners |
| Archive/rollback | ELEKS + HCSC | Cutover Owner | Repo Owner, HCSC GitHub Admin |

# 14. Key Risks Reflected in the Workbook

## Identity mapping risk

Source App IDs, tenant IDs, service principals and group identities are not portable simply because repository content migrates.

Mitigation: pre-build the logical IAM model, then perform target App ID remap and update GitHub/external references.

## Incomplete automation coverage

GitHub Apps, OAuth policies, IP allowlists, deploy keys, audit settings, repository variables and full environment controls require manual handling or separate automation.

Mitigation: prepare runbooks and owners before cutover.

## Secret migration exceptions

Custom CyberArk automation restores secrets, but failures, skipped items, visibility rules or repository mapping issues can remain.

Mitigation: make post-migration secret validation and exception remediation an explicit gate.

## Runner migration gap

Runner infrastructure is not migrated.

Mitigation: create the target runner platform before cutover and bind repositories after migration.

## No normal delta migration

GEI does not provide the workbook's required delta model for continuing source changes.

Mitigation: tightly control the cutover window, archive after validation, and use selective source unarchive only as a continuity fallback.

## External integration breakage

Webhooks, deploy keys, GitHub Apps, OIDC and external trust can fail independently of repository migration success.

Mitigation: validate actual application/workflow behavior, not only configuration presence.

# 15. Definition of Done

The GitHub migration should be considered complete only when all critical scope satisfies the following:

Target repositories and supported metadata/configuration are present.

Destination IAM groups, roles, App IDs and service principals are mapped.

Critical repository/team permissions are correct.

Organization, repository and environment secrets are restored and usable.

Required packages are available.

Critical workflows run on intended HCSC runners.

Repository variables and environment protections are restored.

Required webhooks, deploy keys and GitHub Apps function correctly.

OAuth, IP and audit controls meet the approved HCSC policy.

Applications authenticate/authorize correctly using HCSC identities/trust.

Required mannequin attribution is reclaimed or exceptions are documented.

Migration evidence and exceptions are recorded.

HS source repositories are archived only after validation.

Selective rollback/unarchive and resynchronization procedures are documented.

# 16. Jira / Risk Traceability from the Workbook

The workbook associates the migration with the following primary work/risk references:

DEVOPS-14690 — IAM / SCIM readiness

DEVOPS-14692 — migration/access reconciliation

DEVOPS-14830 — core migration and multiple custom/post-migration activities

DEVOPS-14831 — organization configuration

DEVOPS-14832 — runners

DEVOPS-14839 — environment controls

DEVOPS-14840 — deploy keys

DEVOPS-14841 / 14842 / 14843 — GEI-supported configuration areas

DEVOPS-14844 — GitHub Apps

DEVOPS-14845 / 14846 / 14847 — OAuth / IP allowlist / audit controls

DEVOPS-14848 — source archive / rollback

R-005 / R-006 — security/connectivity/audit-related risks

R-008 — SCIM/external-group mapping risk

R-013 — GitHub Apps risk

R-015 — archive/rollback risk

R-019 — IAM / identity mapping risk

R-021 — authentication/external identity reference risk

# 17. Practical Migration Sequence for a Cutover Runbook

### Before the migration window

Freeze/approve the IAM model and ownership register.

Create HCSC roles/groups.

Prepare SCIM/external-group mappings and destination teams.

Provision/validate runner groups, runners, network and capacity.

Complete runbooks for every manual gap.

Confirm migration permissions and cutover owners.

### During the migration window

Control source changes according to the cutover plan.

Run GEI core migration.

Capture GEI logs/results and identify failures.

Validate supported migrated repository configuration.

### Immediately after GEI

Restore secrets through CyberArk.

Migrate packages.

Apply organization rulesets/variables/custom properties.

Reconcile teams, external groups and repository permissions.

Begin mannequin reclamation.

### Post-migration remediation

Remap target App IDs/service principals/groups.

Replace source identity references in workflows/repos/environments.

Bind target runners.

Restore repository Actions variables.

Restore environment controls.

Re-enable/test webhooks.

Replace deploy keys.

Validate secrets and remediate FAILED/SKIPPED exceptions.

Install/reconfigure GitHub Apps.

Restore OAuth/IP/audit controls.

Update external trust and OIDC/application identity dependencies.

### Validation and closure

Execute critical workflows and application tests.

Obtain owner acceptance for critical repositories/applications.

Record exceptions and remediation owners.

Archive validated HS repositories.

Use selective source unarchive only for failed destination repositories according to the rollback procedure.

## Final Interpretation

The workbook defines a migration strategy in which GEI provides the core data movement, custom scripts restore key platform capabilities, and manual activities complete the destination-specific security and application configuration.

The practical critical path is therefore governed less by repository transfer time and more by the chain from HCSC IAM authorization readiness → destination repository creation → access/secrets/runners/identity remediation → functional validation → source archive.

For cutover management, the strongest success metric is not “all repositories migrated.” It is:

All critical HCSC repositories, workflows, identities and integrations are operational and validated, with no unresolved blocking access/secret/authentication issue, before the corresponding HS sources are archived.